# Software Project Management Plan (SPMP)

Engineering (Beemo)

2026-07-17

# Software Project Management Plan

AI-Powered IT Asset & Service Management System — codename “SccIT”

Management authority. This SPMP governs how the project is planned, executed, controlled, and closed. The Software Requirements Specification (SCCIT-SRS v1.0, approved) defines what is built; the Software Design Description (SCCIT-SDD v1.0, approved) defines how it is designed. This plan references those documents by ID and does not restate requirements or design. Where a project detail is not yet fixed, it is recorded as a labelled Assumption (SA-nn) to be confirmed at plan approval.

## Document Control

Table …. Document Control

| Field | Value |
| --- | --- |
| Document ID | SCCIT-SPMP |
| Version | 1.0 |
| Date | 2026-07-17 |
| Status | Waiting for Client Approval |
| Standard | ISO/IEC/IEEE 16326:2019 (and IEEE 1058 heritage) |
| Prepared by | Engineering |
| Owner / decision authority | Client / Product Owner — project owner, system owner, and primary decision-maker |
| Primary inputs | SCCIT-SRS v1.0, SCCIT-SDD v1.0, current repository |
| Related artifacts | PRODUCT.md, DESIGN.md, docs/ (DEVELOPMENT, ENVIRONMENT, DOCKER, INSTALLATION, PROJECT_STRUCTURE), .github/workflows/ci.yml, Makefile, scripts/, compose.yaml |

### Revision History

Table …. Revision History

| Version | Date | Author | Summary |
| --- | --- | --- | --- |
| 1.0 | 2026-07-17 | Engineering | Version 1.0 baseline. Consolidated project management plan: purpose and scope, current state, management objectives, deliverables, team roles and responsibilities, lifecycle model, work breakdown structure and work packages, phase plan (P2 Core · P3 AI & Knowledge Base · P4 Interactive Floor Plan & Real-time), milestones, estimation, risk management, quality assurance and verification, configuration and change management, issue management, acceptance, and Appendices A–B. Aligned to SCCIT-SRS v1.0 and SCCIT-SDD v1.0. Status: Waiting for Client Approval. |
| 1.0 | 2026-08-26 | Engineering | Phase 2.5 — Asset Management delivered against the Version 1.0 baseline (label unchanged). WP-2.3 and WP-2.4 marked ✅ done: PC units with the specification editor, serialized assets, the hardware catalog, audited lifecycle transitions, transfers, custodianship, attachments, the unified asset history, QR generate/regenerate/revoke/print, the module dashboard and the enterprise directory. Scope carried forward as WP-2.4b (consumables, stock ledger, procurement, disposal, import/export, bulk actions) and WP-2.4c (QR scan verification), so the remaining FR-AST/FR-QR requirements stay tracked rather than being absorbed silently. |
| 1.0 | 2026-08-28 | Engineering | Phase 2.6 — Ticket Management delivered against the Version 1.0 baseline (label unchanged). WP-2.5 marked ✅ done: the row-scoped visibility model, audited lifecycle with scheduled auto-close, assignment with a database-enforced one-active rule answering 409, comments including internal notes, votes, attachments, SLA derivation, duplicate discovery, the administrative directory and the module dashboard — verified live for all three roles in development and production. Recorded the work-package numbering offset (SPMP WP-2.5 = Phase 2.6) so the two schemes stay legible together, and carried ticket export (FR-RPT-004) and ticket AI (FR-AI-*, P3) forward as tracked rather than absorbing them silently. |
| 1.0 | 2026-08-28 | Engineering | QR workflow clarification recorded against the Version 1.0 baseline (label unchanged), ahead of implementation. Rescoped WP-2.6 to the full Maintenance domain including proof-of-work capture (FR-MNT-009..011); added WP-2.6b — QR-verified technician job workflow, which absorbs the carried-forward WP-2.4c and adds the technician work support request, the administrator decision set and both tracking surfaces (FR-WSR-001..013, FR-QR-010..013). WP-2.4c is retained in the table rather than removed, so its requirement IDs stay traceable. Recorded why the two packages are sequential rather than one milestone, and flagged the WP-2.7 notification dependency as a scheduling decision for the client. No work package was deleted and no version label was changed. |
| 1.0 | 2026-08-28 | Engineering | QR workflow clarification — Client decisions recorded against the Version 1.0 baseline (label unchanged). The two-package structure (WP-2.6 then WP-2.6b, sequential and independently gated) is approved. WP-2.6b rescoped to match the decided design: proof of work attached to an active maintenance record, the six-state controlled transition map including cancelled, the scan-scoped panel under its own policy ability, and the minimum notification channel/service plus the six workflow triggers — the notification centre, preferences UI and digest remaining in WP-2.7, which therefore need not move ahead. OI-08..11 marked resolved in the risk register; WP-2.4c retains its row and its requirement IDs, delivered inside WP-2.6b. |
| 1.0 | 2026-08-28 | Engineering | WP-2.6 Maintenance Domain — Client decisions recorded against the Version 1.0 baseline (label unchanged), ahead of implementation. The FR-MNT-009 split is now explicit in both work-package rows so neither appears to skip it: WP-2.6 owns the Maintenance-side foundation, WP-2.6b owns the scanned submission and its idempotency (SRS FR-MNT-009, SDD DD-57). Recorded the approved WP-2.6 scope decisions — additive migrations only, no maintenance_status_history table, no maintenance verification state (none is specified), preventive-maintenance detection and in-app surfacing without notification dispatch, and duplicate maintenance handled as a non-blocking warning rather than a database constraint. Added the DR-022 schema addition to the package. No work package was deleted and no version label was changed. |
| 1.0 | 2026-08-28 | Engineering | WP-2.6 — Maintenance Domain delivered against the Version 1.0 baseline (label unchanged). WP-2.6 marked ✅ done: row-scoped visibility whose list rule and uuid rule are provably the same rule, the audited five-state lifecycle with the PC-unit effect, checklists with required-item enforcement, repair evidence through the existing attachment trust boundary, notes, hardware replacements reconciling the installation history, preventive due detection on the configured cadence, and the technician and administrator surfaces — verified live for all three roles in development, with the production image rebuilt and its structural parity confirmed. Four additive migrations (24 → 28). Carried forward as tracked rather than absorbed: the scanned submission and its idempotency to WP-2.6b, and notification delivery for maintenance triggers to WP-2.6b/WP-2.7. |
| 1.0 | 2026-08-30 | Engineering | WP-2.6b — QR-verified technician job workflow delivered against the Version 1.0 baseline (label unchanged). WP-2.6b marked ✅ done for its functional scope, and WP-2.4c closed as absorbed: authenticated scan entry with non-disclosing pre-authentication answers and per-client/per-account rate limiting; the scan-scoped PC panel under its own policy ability; proof of work with six-layer idempotency on the scan; work support requests on the six-state map; the three administrator decisions with a database-enforced decline reason; both tracking surfaces plus authorized evidence retrieval. Two additive migrations (28 → 30). Carried forward as tracked rather than absorbed: the minimum notification channel/service and its workflow triggers named in this work package’s own scope (FR-WSR-012, partial FR-NOT-003, DD-52) move to WP-2.7, together with the notification centre and preferences that always belonged there; the procurement bridge (FR-WSR-013) and automatic support-request closure remain open. Recorded as deferred / carried forward, not implemented: the notification centre, notification preferences and email delivery; the minimum notification channel and its workflow triggers (FR-WSR-012, partial FR-NOT-003, DD-52); the procurement bridge (FR-WSR-013); automatic support-request closure; axe/WCAG regression automation; browser visual regression; the two pre-existing Phase 2.4/2.5 factory-collision test flakes; ticket export (FR-RPT-004); ticket AI (FR-AI-*); WP-2.4b; the floor plan; and Phase 2.7. No requirement was removed and no version label was changed. |
| 1.0 | 2026-09-30 | Engineering | WP-M — Admin predictive-maintenance reports delivered against the Version 1.0 baseline (label unchanged). WP-3.4 marked ✅ done for the review surface of FR-AI-011: the Administrator-only list and finding pages, confirm and dismiss, the administrator notification through the existing infrastructure, and Pest, Vitest, Playwright and axe coverage including role-by-role denial and direct-uuid protection. The WP-L generation pipeline was already on the branch; its route, permission, policy and notification wiring, which had been left out of the handoff commit, is completed here. FR-AI-013 is not part of this package. |
| 1.0 | 2026-09-30 | Engineering | WP-P — RAG knowledge indexing delivered against the Version 1.0 baseline (label unchanged). WP-3.2 marked ✅ done for its pipeline and retrieval scope: the chunker, GenerateEmbeddingJob with states, retries and stale detection, the knowledge:index sweep, and a retrieval service over the existing ai_embeddings HNSW index — for the published knowledge articles only, by the client’s instruction that transactional records stay out of the shared vector index. Not delivered and not claimed: knowledge-article authoring/review screens, any HTTP route over retrieval, and starter article content (none was invented). Numbering note: WP-3.2 is the SPMP identifier; “WP-P” is the conversational package name. |

1.0 | 2026-09-06 | Engineering | WP-2.7d — Quality & operational foundation delivered against the Version 1.0 baseline (label unchanged). Added a WP-2.7d row to the §10 WBS, marked ✅ done: reproducible production deployment with immutable prod-<sha> image tags, release manifests and pre-deploy database snapshots; retention and a scripted rollback; the committed Playwright browser harness with deterministic fixtures; axe accessibility regression automation against a committed baseline; documented quality gates and a production-target smoke suite. Annotated WP-2.11 so this early delivery is not mistaken for hardening completion — the full WCAG 2.2 AA conformance audit, performance and load testing, browser visual regression, the security review and the first authorized production deployment all remain outstanding there. Extended §21 with the release and rollback tooling and the distinction the sign-off insisted on: the tooling is implemented and verified to fail safe, but no real production rollback has ever been exercised, releases/ is absent, no prod-<sha> tag exists, and the surviving pre-WP-2.6b images predate the convention and cannot be used by the new scripts. No work package was deleted and no version label was changed. |
1.0 | 2026-09-06 | Engineering | WP-2.7a — Notification infrastructure delivered against the Version 1.0 baseline (label unchanged). Decomposed the single WP-2.7 row into its delivery sub-packages, following the WP-2.6b precedent, and added WP-2.7a ✅ done: the project channel driver over the baselined schema, the dispatcher with per-recipient failure isolation, audience resolution through each domain’s own visibility rule, the opt-out preference gate, trigger identity, idempotency via dedupe_key, SLA breach detection, the eight-endpoint API, and nine of FR-NOT-003’s twelve triggers. Recorded one additive migration (30 → 31) and the T7/T8 carry-forward to WP-2.4b, whose row now states that it blocks those two triggers and the FR-WSR-013 bridge. Marked the WP-2.6b notification carry-forward discharged. Added WP-2.7c (announcements) and WP-2.7e (digest) as not started, and recorded that D5 makes WP-2.7c depend on WP-2.7a because publishing an announcement notifies in-app. No work package was deleted and no version label was changed. |
1.0 | 2026-09-06 | Engineering | WP-2.7b — Notification experience delivered against the Version 1.0 baseline (label unchanged). Added WP-2.7b ✅ done: the notification centre at /app/notifications, the top-bar entry with its unread badge and dropdown panel, individual and bulk read/unread with optimistic rollback, filtering by unread state and by type, pagination, and the channel × type preference matrix on /app/account — frontend only, with no backend, schema or migration change. Extended the §11 delivery record through phases 2.5, 2.6, 2.6b and 2.7, and stated the environment divergence plainly: repository, development and test carry 31 migrations while production carries 30, because Phase 2.7 is committed but not deployed. Recorded that the a/b/c/d suffixes are delivery-order sub-packages rather than a second numbering scheme, and that they were delivered out of alphabetical order — WP-2.7d first, because the harness had to exist before the surfaces it verifies. No work package was deleted and no version label was changed. |
1.0 | 2026-09-07 | Engineering | WP-2.7c — Announcements delivered against the Version 1.0 baseline (label unchanged). Marked WP-2.7c ✅ done in the WBS: the management surface behind the existing system.announcements.manage, the reader at /app/announcements, audience targeting enforced as an authorization boundary at the uuid as well as in the list, and the SRS FR-NOT-003 announcement trigger. Delivered as forecast — one NotificationTopic case and one listener, no new permission and no schema change — with one addition the plan did not anticipate: the SDD DD-66 channel-exclusion mechanism, needed because the opt-out preference gate could not by itself guarantee that publishing sends no email. Recorded that FR-NOT-003 now stands at ten of twelve triggers; the remaining two stay blocked on WP-2.4b and their status is unchanged. Noted WP-2.7e (the FR-NOT-008 digest) as the one outstanding WP-2.7 sub-package. The package is committed but not deployed, so the environment-divergence note stands. No work package was renumbered and no version label was changed. |
1.0 | 2026-09-07 | Engineering | WP-2.7e — Daily digest delivered against the Version 1.0 baseline (label unchanged). Marked WP-2.7e ✅ done, closing the last outstanding WP-2.7 sub-package: the digest was delivered as the third delivery channel D1 approved, on a 07:00 Asia/Manila schedule covering the previous school-local calendar day, with at-most-once delivery enforced by a new notification_digests table unique on (user_id, digest_date) — the one addition beyond the original design, and approved as such before implementation. Recorded FR-NOT-008 satisfied in the SRS and amended SDD DD-63 in place. Updated the environment-divergence note: the repository now carries 32 migrations against production’s 30, and because Laravel applies pending migrations in filename order, the first production deployment of WP-2.7e is necessarily also the first of WP-2.7a, WP-2.7b and WP-2.7c. FR-NOT-003 triggers 7 and 8 remain blocked on WP-2.4b and their status is unchanged. No work package was renumbered and no version label was changed. |
1.0 | 2026-10-18 | Engineering | WP-2.10 progress — Phase 2.10 R0–R3 recorded against the Version 1.0 baseline (label unchanged; SPMP WP-2.10 is conversational Phase 2.10, which also carries the asset-import slice of WP-2.4b). Delivered: R0 report and chart libraries locked through disposable gate containers (owner decision D7); R1 the Administrator’s filterable ticket overview (FR-DSH-009); R2 overlay hardening and shared primitives; R3 report export, email and print (FR-RPT-004/008/009), deployed 2026-10-18 (01238a6); R4 Overall Reports (FR-RPT-010), deployed 2026-10-18 (29ae9f0); R5 AI interpretations (FR-RPT-011, off by default), deployed 2026-10-18 (0c0a57b); R6 asset import (FR-AST-016; the asset-import slice of WP-2.4b), deployed 2026-10-18 (9f151fb); R7 post-import review (FR-AST-017). R0–R2 deployed to production on 2026-10-18 (096132e). Phase 2.10 (R0–R7) is complete. The rest of WP-2.4b (consumables, stock, procurement, disposal, export, bulk actions) is unchanged. |
1.0 | 2026-10-19 | Engineering | Phase 2.11 — Floorplan completion and the PC status model delivered against the Version 1.0 baseline (label unchanged). Numbering note: “Phase 2.11” is conversational; the SPMP work packages are WP-4.1/4.2/4.3. Marked WP-4.1 ✅ (WP-A, plus the presence channel), WP-4.2 ✅ (the Floorplan editor) and WP-4.3 ✅ for its functional scope (status model, details panel, realtime, position release), with GA pending owner acceptance on production and the CI browser run. Two migrations (S: PC status model with its audited data mapping and archive of retired PCs; F1: layout revision, workstation rotation rule, fixtures table). No work package was deleted and no version label was changed. |
1.0 | 2026-10-19 | Engineering | Phase 2.11 — pre-deployment verification recorded against the Version 1.0 baseline (label unchanged). WP-4.3 annotated with the verification evidence: the status migration’s rollback is exact and was rehearsed twice on a verified production copy; the full browser suite and the full accessibility project pass in a disposable stack (the DonutChart aria-hidden-focus regression and the e2e project’s broken json import, both pre-existing, were fixed). GA still waits on the owner’s production acceptance. No work package was deleted and no version label was changed. |
1.0 | 2026-10-19 | Engineering | Phase 2.11 follow-up — owner requests of 2026-10-19 recorded against the Version 1.0 baseline (label unchanged). Numbering note: conversational “Phase 2.11 follow-up”; it amends delivered packages WP-2.1, WP-2.2, WP-2.3/2.4, WP-2.5, WP-2.6b and WP-2.7c and adds none. Added a note under the §10 WBS: post-sign-in destination (SDD DD-105), comment edit/remove rules (DD-106), announcement Publish (DD-107), derived building codes (DD-108), internal asset tag and optional asset fields (DD-109), full name with middle name, and presentation fixes. Implemented and verified locally; not deployed and not pushed — deployment pending owner approval. No work package was deleted, no status was changed and no version label was changed. |
1.0 | 2026-10-20 | Engineering | Production readiness (conversational “production-readiness plan”; SPMP WP-2.11 P2 hardening / security review / prod deploy) recorded against the Version 1.0 baseline (label unchanged). Release 2.11.0 reconciled into main by a reviewed merge commit (first GitHub CI run since 2026-07-07; CI-only fixes). Security hardening: committed credential fallbacks removed and the exposed production passwords rotated; secret redaction in logs and failed jobs; health endpoint, seeders and deploy guards hardened; gitleaks in CI. SMTP2GO readiness (environment-only, TLS required, diagnostics, queued account mail). Render free-tier pilot packaging with synthetic data only — not a production deployment (SDD DD-110…DD-113, docs/RENDER_PILOT.md). |
1.0 | 2026-10-20 | Engineering | Owner requests of 2026-10-20 (conversational; no new SPMP work package — recorded under the Phase 2.11 follow-up maintenance line) recorded against the Version 1.0 baseline (label unchanged): add-asset option lists and “Other” fields, every asset-dashboard panel navigable, custodian placement confirmation with confirmed equipment on the Floorplan, the AI concurrency fallback for the Render pilot, report-mail wording, and the in-app QR label scanner (SDD DD-114..DD-117). Two migrations. Delivered by pull request, merged to main, and deployed to local production with deploy-prod.sh; real-device scanner checks and the SMTP2GO sender-domain verification remain with the owner. |

### Conventions

- Identifiers: deliverables DL-nn; milestones M0..Mn; work packages WP-<phase>.<n>; project/management risks PR-nn (product/technical risks are inherited from SRS §32 RSK-01..10); assumptions SA-nn; roles R-xxx.

- Phasing matches the SRS/SDD exactly: P2 Core · P3 AI & Knowledge Base · P4 Interactive Floor Plan & Real-time · Future.

- Effort sizing uses relative T-shirt sizes (S ≤ 3 dev-days · M ≤ 1 sprint · L ≈ 1–2 sprints · XL > 2 sprints). Calendar figures are indicative and depend on confirmed team capacity (SA-01).

- Reference markers FR-*, NFR-*, DD-*, RES-*, RSK-* point to the identically-named items in the SRS/SDD.

## Table of Contents

…

## List of Tables

…

## 1. Executive Summary

SccIT is a production-intended, vertical-agnostic ITSM/ITAM platform. Its foundation is already built and verified: a fully Dockerized Laravel 13 + React 19 stack, a production-grade PostgreSQL 17 data layer (66 models, integrity enforced in the database), and a green CI pipeline (phases 0–7). The requirements (SRS) and design (SDD) are complete and are Waiting for Client Approval. This SPMP governs the remaining lifecycle: building the application layer across three phases — P2 Core, P3 AI & Knowledge Base, P4 Interactive Floor Plan & Real-time — followed by steady-state maintenance.

The project runs an iterative, phase-gated model that matches the established working agreement: work proceeds in short sprints inside each phase, and each phase ends at a client approval gate before the next begins. Quality is non-negotiable and largely automated — every change passes the same gates CI already enforces (Pint, Larastan level 6, Pest; ESLint, Prettier, TypeScript, Vitest, build) — and correctness is backstopped by database constraints, so the “done” bar is objective and repeatable.

Management is deliberately lightweight but disciplined: trunk-based Git with short-lived reviewed branches, a WBS decomposed by the SDD’s domains, milestones defined by acceptance rather than dates, and a risk register that inherits the SRS’s technical risks and adds project-level ones (schedule, bus-factor, AI-provider dependency, client-gate availability). Because the team size and cadence are not yet fixed, all calendar figures are presented as clearly-labelled assumptions to be confirmed at approval; the structure of the plan (sequencing, gates, quality bar, deliverables) is firm.

## 2. Project Overview

### 2.1 Context

SccIT replaces manual, fragmented IT operations with a single platform for asset management, service ticketing, preventive maintenance, QR verification, AI-assisted troubleshooting, and analytics (see SRS §1–§6). It is single-tenant, deployed first for an educational institution, and re-brandable to any organization via settings (BO-08).

### 2.2 What this plan manages

The build-out of the application layer (P2 → P3 → P4), its verification and release to production, and its ongoing maintenance — governed by the SRS/SDD and executed with the tooling already in the repository.

## 3. Objectives

The project succeeds when the specified requirements are delivered to production at the stated quality bar. Management objectives (traceable to SRS §5 BO-01..08):

Table …. Objectives

| ID | Management objective | Measure of success |
| --- | --- | --- |
| PO-1 | Deliver P2 Core to production meeting all P2 acceptance gates. | SRS §31 AC-G1..G6 pass; client sign-off at M5. |
| PO-2 | Deliver P3 AI and P4 Floor Plan behind their own gates. | P3/P4 acceptance pass; M6/M7 sign-off. |
| PO-3 | Keep quality automated and continuous. | CI green on every merge; ≥ 80% domain test coverage (NFR-MTN-005). |
| PO-4 | Hold the security & accessibility bar as a release gate, not an afterthought. | Security review + WCAG 2.2 AA audit pass each phase (SRS §12, §16). |
| PO-5 | Manage risk and change transparently against the current baselines. | Risk register reviewed each sprint; changes go through §25. |
| PO-6 | Preserve maintainability and knowledge for the long term. | Docs current in the vault; ADRs recorded; onboarding ≤ 1 day. |

## 4. Scope

### 4.1 Management scope of this plan

Planning, execution, monitoring/control, and closure of the application build (P2–P4) plus transition to maintenance. It covers process, people, schedule, quality, risk, configuration, release, and operations — not the product requirements (SRS) or the technical design (SDD).

### 4.2 Product scope (by reference)

In-scope and out-of-scope product capabilities are defined authoritatively in SRS §3. Summary: P2 delivers the core ITSM/ITAM platform; P3 adds AI/RAG; P4 adds the interactive floor plan and real-time. Explicitly out of scope: ERP/LMS/RMM functions, native mobile apps, and multi-tenancy (SRS §3.3, CON-08).

### 4.3 Scope control

Scope is baselined by the SRS. Additions or changes follow §25 Change Management; the seven open product decisions (SRS §33 OI-01..07) are tracked as pending change items and must be resolved before they affect a phase they touch.

## 5. Deliverables

Table …. Deliverables

| ID | Deliverable | Phase | Acceptance basis |
| --- | --- | --- | --- |
| DL-01 | Software Requirements Specification (SRS) | Docs | Waiting for Client Approval |
| DL-02 | Software Design Description (SDD) | Docs | Waiting for Client Approval |
| DL-03 | Software Project Management Plan (SPMP, this document) | Docs | Waiting for Client Approval |
| DL-04 | P2 Core application (all P2 FRs) + API (OpenAPI) | P2 | SRS §31 P2 gates |
| DL-05 | Design-system component library + accessible SPA shell | P2 | NFR-USB, NFR-ACC |
| DL-06 | Automated test suites (Pest + Vitest) ≥ 80% domain coverage | P2+ | NFR-MTN-005 |
| DL-07 | Production deployment (staging + prod) + runbooks | P2 | §26 |
| DL-08 | Backup/restore + monitoring operational | P2 | §27, §28 |
| DL-09 | Security review report + WCAG 2.2 AA audit report | each phase | §29, §30 |
| DL-10 | P3 AI & Knowledge Base (RAG) | P3 | SRS §17 gates |
| DL-11 | P4 Interactive Floor Plan + real-time | P4 | SRS §19 gates |
| DL-12 | User & administrator documentation | P2+ | §17 |
| DL-13 | Maintenance & support handover pack | post-P2 | §31 |
| DL-14 | Updated ADRs and engineering docs in the vault | continuous | §17 |

## 6. Stakeholders

Stakeholders and their interests are defined in SRS §7. Management-relevant responsibilities:

Table …. Stakeholders

| Stakeholder | Project responsibility |
| --- | --- |
| Client / sponsor | Funds the project; approves phase gates; owns the open product decisions (SRS §33); provides UAT participants. |
| Product owner (client-side) | Prioritizes backlog within defined scope; signs off acceptance. |
| Engineering team | Delivers, tests, documents, and operates the system (§7). |
| IT Administrators (end org) | UAT, operational readiness, production configuration/branding. |
| Data-protection / security owner | Reviews AI data governance (SRS §17.5) and security posture. |
| End users (technicians, teachers) | UAT feedback; usability validation. |

## 7. Team Roles and Responsibilities

[SA-02] The delivery team is small; one person may hold several roles (the repository currently shows a single primary contributor). Roles below are functions, mapped to people at approval. AI pair-assistance (Claude Code) is used under human review — it never bypasses the code-review or acceptance gates.

Table …. Team Roles and Responsibilities

| Role | Code | Responsibilities |
| --- | --- | --- |
| Project Manager | R-PM | Plan, schedule, risk/issue tracking, client gate coordination, reporting. |
| Developer | R-DEV | Guards SRS/SDD conformance; reviews and owns design decisions and ADRs; final code-review authority. Laravel domains (Services/Actions/Models), migrations, API, jobs; React feature slices, design-system components, accessibility; CI/CD, environments, deployment, backup/monitoring, release cutovers; security reviews, secrets/dependency management, incident response; DESIGN.md conformance, usability, WCAG validation; tests for all of the above. |
| QA | R-QA | Test strategy, acceptance test execution, coverage, regression, a11y/perf verification. |

RACI (condensed): R-PM accountable for schedule/risk; R-DEV accountable for technical conformance; R-QA accountable for acceptance verification; client accountable for gate approvals. All roles responsible for tests and docs of their work.

## 8. Development Methodology

### 8.1 Model

Iterative & incremental, phase-gated, matching the established working agreement (analyze → approve → plan → approve → implement, verifying each increment; never leave the project broken). This is a Scrum-lite/Kanban hybrid:

- Phases (P2/P3/P4) are the major gates; each ends with client acceptance before the next begins.

- Sprints of 2 weeks (SA-03) inside each phase deliver vertical slices (a domain’s API + UI + tests together).

- Kanban flow for defects/small tasks between sprint boundaries.

### 8.2 Definition of Ready (a work item may start when)

Requirement ID(s) identified; acceptance criteria known (SRS §31); design approach clear (SDD reference); dependencies available; test approach agreed.

### 8.3 Definition of Done (a work item is done when)

Code + tests written; CI green (all gates); domain coverage target met; API documented (OpenAPI); accessibility checks pass for UI; security-sensitive paths reviewed; docs/ADR updated; peer-reviewed and merged; demonstrated against acceptance criteria.

### 8.4 Cadence

Sprint planning, sprint review/demo, and retrospective per sprint; short async daily status; phase-gate review with the client at each milestone (§24).

## 9. Project Organization

- Structure: a single cross-functional delivery team building a modular monolith (SDD DD-01); no sub-teams needed at current scale.

- Decision rights: technical decisions → R-DEV (recorded as ADRs in vault/08 ADR, rationale in Claude-Mem per the project’s knowledge model); scope/priority → client product owner; process → R-PM.

- Environments owned by R-DEV: development (Docker on the workstation), staging (production-like), production.

- Knowledge system (per the project’s operating model): codebase graph = what; Claude-Mem = why; auto-memory = how we work; the Obsidian vault = human engineering docs (this plan, SRS, SDD, ADRs).

## 10. Work Breakdown Structure

Decomposed by SDD domain. Effort is relative (SA-01). “New” domains are the P2 additions from SDD RES-01/RES-02.

Table …. Work Breakdown Structure

| WP | Work package | Key requirements (SRS) | Effort | Depends on |
| --- | --- | --- | --- | --- |
| WP-0 | Foundation (Docker, scaffolds, DB layer, CI) | — | ✅ done | — |
| WP-1 | Documentation (SRS, SDD, SPMP; resolve OI-01..11) | SRS §33 | M (in progress) | — |
| WP-2.0 | SPA shell + design system components + theming + a11y baseline | NFR-USB, NFR-ACC, DESIGN.md | L | WP-1 |
| WP-2.1 | Identity & Access domain: Sanctum auth, sessions, lockout, RBAC engine, users | FR-AUTH-, FR-USER-, NFR-SEC-* | L | WP-2.0 |
| WP-2.2 | Locations domain: buildings/floors/rooms CRUD | FR-LOC-* | ✅ done | WP-2.1 |
| WP-2.3 | Assets pt.1: PC units, specifications, QR generate/print | FR-PC-*, FR-QR-001..004/007 | ✅ done | WP-2.2 |
| WP-2.4 | Assets pt.2: catalog, serialized assets, lifecycle, transfers, custodianship, attachments, history, module dashboard + enterprise directory | FR-AST-001/002/005/006/011/012/013/014/015 | ✅ done | WP-2.3 |
| WP-2.4b | Assets pt.3 (carried forward): consumables, stock ledger, procurement, disposal workflow, asset import/export, bulk actions (asset import ✅ delivered as Phase 2.10 R6, FR-AST-016). Also blocks two notification triggers — low-stock reorder and procurement approval/rejection (FR-NOT-003 #7 and #8) have no domain code to fire from, and the FR-WSR-013 procurement bridge waits on the same tables | FR-AST-003/004/007/008/009/010, FR-NOT-003 (triggers 7–8), FR-WSR-013 | L | WP-2.4 |
| WP-2.4c | QR scan verification (carried forward — now delivered inside WP-2.6b): scan endpoint, deterministic result classification, qr_scan_logs, QR-initiated maintenance | FR-QR-005/006/008/009 | ✅ done (inside WP-2.6b) | WP-2.4, WP-2.6 |
| WP-2.5 | Tickets domain: lifecycle, comments, votes, attachments, tags, SLA, duplicates + technician assignment | FR-TKT-, FR-ASN- | ✅ done | WP-2.1, WP-2.2 |
| WP-2.6 | Maintenance domain: corrective + preventive records with row-scoped visibility, checklists and required-item enforcement, repair evidence through the existing attachment boundary, notes, hardware replacements, PM reminders, technician and administrator surfaces | FR-MNT-001..008/010/011, FR-MNT-009 (Maintenance-side foundation — see the split note), DR-021, DR-022 | ✅ done | WP-2.3, WP-2.5 |
| WP-2.6b | QR-verified technician job workflow (absorbs WP-2.4c): authenticated scan entry and return-to-destination, scan-scoped PC panel under its own policy ability, proof-of-work attached to an active maintenance record, technician work support requests on a six-state controlled transition map, the administrator decision set (approve-and-reschedule · request face-to-face · decline with a required reason), technician withdrawal, both tracking pages plus authorized evidence retrieval and the combined submission history, and audit | FR-QR-005/006/008..013, FR-WSR-001..011/014, FR-MNT-009 (scanned submission — see the split note)/010/012, DR-020 | ✅ done (functional scope. The carried-forward notification channel/service and its workflow triggers — FR-WSR-012, partial FR-NOT-003, DD-52 — were discharged by WP-2.7a on 2026-09-05, which built the full infrastructure rather than the planned minimum. The FR-WSR-013 procurement bridge remains open, blocked on WP-2.4b.) | WP-2.6, WP-2.4 |
| WP-2.7 | Administration pt.1: notifications + preferences + announcements. Delivered as four sub-packages (see the rows below), following the WP-2.6b precedent. All five sub-packages are done — WP-2.7d, WP-2.7a, WP-2.7b, WP-2.7c and WP-2.7e | FR-NOT-* | M | WP-2.1 |
| WP-2.7d | Quality & operational foundation: reproducible production deployment with immutable prod-<sha> image tags, release manifests and database snapshots; retention and a scripted rollback; the committed Playwright browser harness with deterministic fixtures; axe accessibility regression automation against a committed baseline; documented quality gates and a production-target smoke suite | NFR-MTN-, NFR-ACC-, SRS §12–§16 | ✅ done | WP-2.6b |
| WP-2.7a | Notification infrastructure: the project database channel driver over the baselined schema (SDD DD-52), dispatcher with per-recipient failure isolation (SDD DD-59), audience resolution through each domain’s own visibility rule, the opt-out preference gate, trigger identity (SDD DD-58), idempotency via dedupe_key (SDD DD-60), SLA breach detection, the eight-endpoint API, and nine of FR-NOT-003’s twelve triggers | FR-NOT-001..006, FR-WSR-012, partial FR-NOT-003 | ✅ done (one additive migration, 30 → 31; T7/T8 carried forward to WP-2.4b; announcements and the digest were out of this package’s scope and were delivered later by WP-2.7c and WP-2.7e) | WP-2.6b, WP-2.1 |
| WP-2.7b | Notification experience: the notification centre at /app/notifications, the top-bar entry with its unread badge and dropdown panel, individual and bulk read/unread with optimistic rollback, filtering by unread state and by type, pagination, and the channel × type preference matrix on /app/account | FR-NOT-001/002/004/005 (UI halves) | ✅ done (frontend only — no backend, schema or migration change) | WP-2.7a |
| WP-2.7c | Announcements: the management surface (compose, publish, withdraw, explicit re-notify, delete) behind the existing system.announcements.manage, the reader at /app/announcements with a per-announcement page, audience targeting enforced as an authorization boundary at the uuid as well as in the list, and the FR-NOT-003 announcement trigger. Decision D5 (2026-09-05): publishing creates an in-app notification and sends no email — held, and enforced by channel exclusion in the dispatch path (SDD DD-66) rather than by the opt-out preference gate. Delivered as forecast: one NotificationTopic case and one listener, no new permission and no schema change | FR-NOT-010/011, FR-NOT-003 (trigger 12) | ✅ done | WP-2.7a |
| WP-2.7e | Daily digest (SRS FR-NOT-008, SDD DD-63): decision D1 approved digest as a third delivery channel, and it was delivered as one — notification_preferences.channel widened to include digest, a DailyDigest service and notifications:send-digest command on a 07:00 Asia/Manila schedule covering the previous school-local calendar day, and at-most-once delivery enforced by a new notification_digests table unique on (user_id, digest_date). The one addition beyond the original design: that table, because a digest writes no notification row and cannot reuse dedupe_key | FR-NOT-008 | ✅ done | WP-2.7a |
| WP-2.8 | Administration pt.2: system settings + branding | FR-CFG-* | M | WP-2.1 |
| WP-2.9 | Administration pt.3: audit + activity log viewers | FR-AUD-* | S | WP-2.1 |
| WP-2.10 | Analytics domain: dashboards + KPIs + on-demand reports + export | FR-DSH-, FR-RPT- | L (role dashboards ✅ done; Phase 2.10: ticket overview ✅, export/email/print ✅, Overall Reports ✅, AI interpretations ✅) | WP-2.5, WP-2.4 |
| WP-2.11 | P2 hardening: security review, WCAG AA audit, perf/load test, backup ops, prod deploy. Partly anticipated by WP-2.7d, which delivered the axe regression automation, the browser harness and the deployment/rollback tooling early. Still outstanding here: the full WCAG 2.2 AA conformance audit (regression ≠ conformance), performance and load testing, browser visual regression, the security review, and the first authorized production deployment | SRS §12–§16 | L | WP-2.2..2.10 |

Note on work-package numbering. The WP numbers above are this document’s and are offset from the phase numbers used in delivery discussions and in the code comments: WP-2.2 = Phase 2.4 (Locations), WP-2.3 + WP-2.4 = Phase 2.5 (Assets), and WP-2.5 = Phase 2.6 (Tickets). Both schemes are correct in their own context; the offset is recorded here so a reader of either does not renumber the other. WP-2.7 and Phase 2.7 coincide; the a/b/c/d suffixes on it are delivery-order sub-packages, following the WP-2.6b precedent, and are not a second numbering scheme. They were delivered out of alphabetical order — WP-2.7d first, because the browser and accessibility harness had to exist before the surfaces it verifies.

WP-2.5 carried forward. Ticket export (FR-RPT-004) and the ticket AI snapshot / AI-assisted triage (FR-AI-*, P3) are deliberately not part of the delivered work package and remain tracked against their own requirements.

WP-2.6 and WP-2.6b are sequential, not one milestone. The QR workflow is a technician workflow, not a scan endpoint: it needs a maintenance record to submit proof against and a job to request resources for. Shipping the scan first would produce exactly the “simple asset lookup” the client has ruled out. Splitting them also keeps the new authorization surface — a Technician reaching a PC unit outside the Administrator-only Asset module (SRS FR-QR-012) — in its own verifiable gate rather than landing alongside the maintenance CRUD. WP-2.4c is not deleted: it is delivered inside WP-2.6b, and its requirement IDs stay traceable.

The FR-MNT-009 split — approved by the Client (2026-08-28). One requirement genuinely spans both packages, so it is split along the line each package can verify on its own rather than being listed twice and drifting, or falling between them because each assumed the other had it. WP-2.6 delivers the Maintenance-side foundation: technician-initiated corrective maintenance where the technician holds maintenance.create, an identifiable active maintenance record for a unit, and the row-scoped rule deciding who may work it. WP-2.6b delivers the scanned entry point, the proof-of-work submission itself and its scan-bound idempotency (SRS FR-MNT-012). Everything in the WP-2.6 half is testable with no scan in existence; everything in the WP-2.6b half is meaningless without a record to attach to — which is SDD DD-50 restated as a schedule (SDD DD-57).

WP-2.6 scope decisions recorded (2026-08-28). Additive, reversible migrations only; no maintenance_status_history table — activity_logs carries the lifecycle timeline (SDD DD-55); no maintenance verification state, because no requirement specifies one; preventive- maintenance due/overdue detection and in-app surfacing only, with notification dispatch remaining WP-2.6b’s minimum channel work; and duplicate maintenance handled as a non-blocking warning at creation rather than a unique constraint, since a machine may legitimately carry a scheduled preventive visit and an active corrective repair at the same time.

Notification sequencing — decided by the Client (2026-08-28). WP-2.6b implements the minimum notification infrastructure its own workflow needs: the project channel driver and dispatch service written to the existing notifications schema (SDD DD-52 — Laravel’s default database schema is not forced onto the project), plus the six triggers of FR-WSR-012 (request submitted; administrator notified; approval with reschedule; clarification requested; decline with explanation; technician notified). The notification centre UI, preferences screen and digest stay in WP-2.7. WP-2.7 does not need to move ahead of WP-2.6b.

Superseded by delivery (recorded 2026-09-06). The paragraph above is the plan of record as approved on 2026-08-28 and is kept for the history. It is not how the work was delivered: WP-2.6b shipped its functional scope and carried the whole notification obligation forward rather than building a minimum channel, and WP-2.7a then built the infrastructure in one package — driver, dispatcher, audience resolution, preference gate, idempotency and nine of twelve triggers. WP-2.7b delivered the notification centre and the preferences screen, so neither is pending. WP-2.7c then delivered announcements and the twelfth trigger, taking FR-NOT-003 to ten of twelve; the two that remain are blocked on WP-2.4b. WP-2.7e then delivered the FR-NOT-008 daily digest, closing the last outstanding WP-2.7 sub-package (SDD DD-63).

Client approvals recorded (2026-08-28). The two-package structure, the authenticated QR entry sequence (SRS OI-08), the dedicated job-scoped support-request entity (SRS OI-09 — procurement_requests neither overloaded nor redesigned, exact schema to be approved before implementation), the record-not-a-calendar treatment of face-to-face clarification (SRS OI-10), and the six-state status vocabulary including cancelled (SRS OI-11) are all approved. WP-2.6b remains gated behind a complete and verified WP-2.6. | WP-3.1 | AI provider + ai_system_settings + ticket triage (async) | FR-AI-001..003/010/014/015 | L | P2 GA | | WP-3.2 | RAG: embedding pipeline + knowledge base + retrieval — ✅ WP-P delivered the embedding pipeline and retrieval service for the published knowledge articles (Source A; FR-AI-006/007). Still open: knowledge-article authoring/review screens (the rest of FR-AI-005) and any HTTP surface over retrieval, which arrives with WP-3.3 | FR-AI-005/006/007 | L | WP-3.1 | | WP-3.3 | Conversational assistant + feedback + duplicate suggestion | FR-AI-004/008/009 | M | WP-3.2 | | WP-3.4 | Predictive maintenance (opt-in, default off) — generation delivered as WP-L, the Administrator review surface and notification as ✅ WP-M (FR-AI-011/012); FR-AI-013 (auto-drafted articles) remains open | FR-AI-011/012/013 | M | WP-3.2 | | WP-3.5 | P3 hardening: AI data-governance verification, security/a11y, GA | SRS §17.5 | M | WP-3.1..3.4 | | WP-4.1 | Reverb + broadcasting infrastructure — ✅ done (Phase 2.8 WP-A; presence channel added in Phase 2.11) | FR-FP-007, FR-NOT-007 | M | P2 GA | | WP-4.2 | Floor-plan editor: layouts, drag/snap positions, keyboard alt — ✅ done as the Floorplan editor (Phase 2.8 WP-C..F; completed in conversational Phase 2.11: edit mode with undo/redo, fixtures, whole-layout save under a revision with per-object merge, room overview) | FR-FP-001/003/009 | L | WP-4.1, WP-2.2/2.3 | | WP-4.3 | Live status/position + info panels; P4 hardening + GA — ✅ functional scope done (Phase 2.8 WP-E/G; Phase 2.11: three-status PC model, details panel, presence, position release). GA pending: owner browser acceptance on production. The full browser suite (73 tests across e2e, incl. the new floor-plan-workflows.spec.ts) and the full a11y project (40) pass in a disposable stack built from the branch; the CI job has not been triggered | FR-FP-002/004/005/007/008 | L | WP-4.2 | | WP-5 | Transition to maintenance: handover, monitoring, restore drill | §31 | M | phase GAs |

Phase 2.11 follow-up — owner requests of 2026-10-19 (implemented and verified locally; NOT yet deployed or pushed). Numbering: “Phase 2.11” is conversational (its floor-plan scope is WP-4.1/4.2/4.3 above); this follow-up adds no work package and changes no package’s status. It amends already-delivered packages: WP-2.1 (full name includes the middle name), WP-2.2 (building code derived from the name — SRS FR-LOC-001, SDD DD-108), WP-2.3/WP-2.4 (asset tag internal and hidden, every add-asset field optional, optional catalog model — FR-AST-002, DD-109), WP-2.5 (only the author edits a comment; Administrators remove — FR-TKT-007, DD-106), WP-2.6b (sign-in lands on the dashboard, which offers the scanned PC instead of resuming it — FR-QR-011, DD-105) and WP-2.7c (the compose form’s Publish — FR-NOT-010, DD-107), plus presentation-only dashboard and layout fixes (SDD §27). No migration. Deployment to production (:8081) is pending the owner’s approval; until then the behaviour exists only in the working tree, and the phase rule that a change is verified only once confirmed on :8081 still applies.

## 11. Phase Plan

Calendar is indicative (SA-01); sequencing and gates are firm. Baseline start: after SPMP approval (≈ 2026-07).

Table …. Phase Plan

| Phase | Focus | Work packages | Indicative duration | Gate |
| --- | --- | --- | --- | --- |
| Docs | SRS/SDD/SPMP + resolve OI-01..07 | WP-1 | ~complete | M0 |
| P2 Core | Full ITSM/ITAM platform to production | WP-2.0 … WP-2.11 | ~10–14 sprints (5–7 mo) | M2–M5 |
| P3 AI/KB | Gemini triage + RAG assistant + KB | WP-3.1 … WP-3.5 | ~4–6 sprints (2–3 mo) | M6 |
| P4 Floor Plan | Interactive floor plan + real-time | WP-4.1 … WP-4.3 | ~3–4 sprints (1.5–2 mo) | M7 |
| Maintenance | Steady-state support & evolution | WP-5 + ongoing | continuous | M8 |

Intra-P2 sequencing: shell + identity first (WP-2.0/2.1) because every screen needs auth, RBAC, and the design system; then the location foundation (WP-2.2); then value-generating domains (Assets, Tickets, Maintenance) in parallelizable slices; then cross-cutting admin/analytics; then hardening. Each domain slice ships API + UI + tests together (vertical slices), keeping the app demoable every sprint.

Delivery to date (implementation phases). The build has been delivered as numbered increments, each ending green and demoable: 2.1 SPA shell + public entry (WP-2.0) · 2.2 authentication & authorization (WP-2.1a) · 2.3 user management (WP-2.1b) · 2.4 Location Management plus the role-dashboard slice of WP-2.10, brought forward at the client’s request so each role has a purposeful landing surface while the operational domains are built. Reporting and export stay in WP-2.10; per-user dashboard customization (FR-DSH-002/006) is deferred with them. Bringing the dashboards forward carried little risk because they only read existing tables — no new schema, and the panels grow richer as each later domain lands. · 2.5 Asset Management (WP-2.3 + WP-2.4) · 2.6 Ticket Management (WP-2.5) · 2.6b the QR-verified technician job workflow, absorbing WP-2.4c · 2.7 the Administration domain’s notification stack, delivered as WP-2.7d (quality and deployment foundation), WP-2.7a (notification infrastructure), WP-2.7b (notification experience), WP-2.7c (announcements) and WP-2.7e (the FR-NOT-008 daily digest).

Environment divergence, stated plainly. The repository, development and test databases carry 32 migrations; production carries 30. Phase 2.7 has been committed but not deployed — neither the WP-2.7a dedupe_key migration nor WP-2.7e’s digest migration has run against production, and the production image predates every Phase 2.7 commit. The gap is now two migrations, and they arrive together: Laravel applies pending migrations in filename order, so the first production deployment of WP-2.7e is necessarily also the first of WP-2.7a, WP-2.7b and WP-2.7c. Nothing in this plan should be read as claiming those packages are live.

## 12. Milestones

Milestones are acceptance-defined (entry/exit criteria), not date-defined.

Table …. Milestones

| ID | Milestone | Exit criteria |
| --- | --- | --- |
| M0 | Documentation baseline approved | SRS + SDD + SPMP signed off; OI-01..07 decisions logged. |
| M1 | App foundation | Auth + RBAC working; SPA shell + design system; a11y baseline; CI green. |
| M2 | Core inventory | Locations, PC units, QR, assets, consumables, stock — CRUD + tests. |
| M3 | Service delivery | Ticketing lifecycle + assignment + maintenance (incl. preventive) end-to-end. |
| M4 | P2 feature-complete | Notifications, settings/branding, audit, dashboards, reporting/export complete. |
| M5 | P2 Core GA | SRS §31 AC-G1..G6 pass; security review + WCAG AA audit + load test pass; UAT sign-off; deployed to production. |
| M6 | P3 AI GA | AI triage + RAG assistant + KB pass SRS §17 acceptance incl. data-governance; graceful degradation verified. |
| M7 | P4 Floor Plan GA | Editor + real-time + info panels pass SRS §19; drag a11y alternative verified. |
| M8 | Steady state | Handover pack delivered; restore drill passed; maintenance cadence active. |

## 13. Development Workflow

The workflow is already established in the repo (docs/DEVELOPMENT.md) and is adopted as-is:

- Environment: everything runs in Docker; make up/down/logs/ps, HMR via Nginx on :8080, Mailpit on :8025.

- Backend feature (intended flow): create classes under app/Domains/<Domain>/…, routes in routes/api.php, migrations in database/migrations/; run artisan/composer inside the app container.

- Frontend feature: create a slice under src/features/<feature>/, call the API via src/services/api.ts (Sanctum cookies automatic).

- Verify locally: make lint && make test (Pint + Larastan + ESLint; Pest + Vitest) before opening a PR.

- Branch → PR → CI → review → merge (§14–§16).

(Command reference: Appendix A.)

## 14. Git Workflow

- Trunk-based on main with short-lived branches; main is always releasable and CI-green.

- Conventional Commits (already used in history: feat:, fix:, chore:, docs:) for readable history and changelog generation.

- Every change via Pull Request; direct pushes to main are disallowed (branch protection — SA-04).

- CI is the merge gate: the backend and frontend jobs in .github/workflows/ci.yml must pass.

- Squash-merge to keep main linear; PR title becomes the conventional-commit subject.

- Release tags vX.Y.Z mark phase GAs and patches (§21).

- LF line endings enforced via .gitattributes; secrets never committed (.env* gitignored).

## 15. Branching Strategy

Table …. Branching Strategy

| Branch | Purpose | Lifetime | Merges to |
| --- | --- | --- | --- |
| main | Single source of truth; always releasable. | permanent | — |
| feature/<slug> | New capability (a WBS slice). | short (≤ a few days) | main via PR |
| fix/<slug> | Bug fix. | short | main via PR |
| chore/<slug> / docs/<slug> | Tooling/config/docs. | short | main via PR |
| release/<x.y> (optional) | Stabilization before a GA if a freeze is needed. | temporary | main + tag |
| hotfix/<slug> | Urgent production fix. | very short | main (+ tag) |

Long-lived divergent branches are avoided (trunk-based). Feature flags / settings toggles (e.g. AI feature switches in ai_system_settings, system_settings) are preferred over long branches for incomplete features.

## 16. Code Review Process

- Every PR reviewed by at least one engineer other than the author (R-DEV is the escalation/authority for architecture-affecting changes).

- Automated first: CI must be green before human review; reviewers do not spend time on style (Pint/Prettier) or type errors (Larastan/tsc) — the pipeline owns those.

- Review checklist: conforms to SRS requirement(s) and SDD design; coding standards (SDD §33); security-sensitive paths (authz, input, secrets, file upload) scrutinized; accessibility for UI; tests present and meaningful; API documented; no id leakage (uuid-only); DB constraints respected; docs/ADR updated.

- Tooling assist: the repo’s code-review tooling may be run on a diff for an extra pass; the security-review tooling is run on security-sensitive PRs. These augment, never replace, human review.

- Merge: author addresses comments; reviewer approves; squash-merge.

## 17. Documentation Strategy

Documentation is a first-class, versioned deliverable, homed in the Obsidian vault and the repo docs/.

Table …. Documentation Strategy

| Doc type | Location | Owner | Cadence |
| --- | --- | --- | --- |
| SRS / SDD / SPMP | vault/01 Project, vault/02 Architecture | R-DEV/R-PM | Versioned; change-controlled (§25). |
| ADRs (decision records) | vault/08 ADR | R-DEV | Per significant decision. |
| API contract (OpenAPI) | backend/ (generated) | R-DEV | Kept in sync per PR (NFR-MTN-006). |
| Developer/ops docs | docs/ (DEVELOPMENT, ENVIRONMENT, DOCKER, INSTALLATION) | R-DEV | Updated with process/infra changes. |
| User & admin guides | vault + delivered docs (DL-12) | R-DEV/R-QA | Per phase GA. |
| Rationale / “why” | Claude-Mem (project knowledge) | team | Continuous. |

Rule: a PR that changes behavior updates the relevant doc in the same PR (Definition of Done). Requirements/design docs are referenced, not copied, to prevent drift.

## 18. Testing Strategy

Realizes SRS §31 acceptance and NFR-MTN-001/002/005; mirrors the SDD test pyramid (SDD §32).

Table …. Testing Strategy

| Level | Scope | Tooling | Gate |
| --- | --- | --- | --- |
| Static | Formatting, style, types, dead code. | Pint --test, Larastan L6, ESLint, Prettier --check, tsc -b. | CI |
| Unit | Actions/services, enums, value logic; React hooks/components. | Pest, Vitest + Testing Library. | CI |
| Integration/Feature | HTTP endpoints, authorization matrix, DB constraint behavior (negative CHECK/trigger cases), Sanctum auth flows. | Pest (Postgres *_test DB), pest-plugin-laravel. | CI |
| Contract | API responses match OpenAPI; uuid-only; error envelope. | Pest resource tests. | CI |
| Accessibility | WCAG 2.2 AA, both themes, keyboard/SR. | automated axe-style scan + manual. | phase gate |
| Performance/Load | Meets SRS §13–§14 targets at nominal load. | load simulation + query-plan analysis. | phase gate |
| Security | SRS §12 controls; dependency + secret checks. | security review + scanners. | phase gate |
| UAT | Business acceptance by client users. | scripted scenarios (SRS §26–§27). | phase gate |

- Coverage target: ≥ 80% line coverage of domain logic for P2 (NFR-MTN-005); tracked in CI.

- Test data: factories (66) + seeders; the DemoSeeder never runs in production.

- Backend tests run against the dedicated school_it_service_management_test DB (phpunit.xml), identical to CI.

## 19. Quality Assurance Plan

- Prevention over detection: the same gates run locally (make lint && make test) and in CI on every push/PR to main — no change merges without them.

- Objective “done” bar: Definition of Done §8.3 + SRS §31 global gates AC-G1..G6.

- Database as a QA backstop: integrity is enforced by FK/CHECK/partial-unique/trigger constraints (SDD §8, DR-002/005/012), so whole classes of defects are impossible to merge.

- Quality metrics tracked per sprint: CI pass rate, coverage %, open-defect count by severity, escaped-defect count, a11y violations (target 0), performance p95 vs targets.

- Phase quality gates: security review + WCAG AA audit + load test + UAT must pass before a phase GA (WP-*.hardening packages).

- Continuous dependency hygiene: composer.lock/package-lock.json pinned; periodic update + vulnerability scan (§29).

## 20. Configuration Management

- Source control: Git; main protected; tagged releases (§14, §21).

- Environment configuration: .env (root, Docker) and backend/.env (Laravel) from tracked *.example templates; real .env* are gitignored (docs/ENVIRONMENT.md). Key production settings: CACHE_STORE=redis, SESSION_DRIVER=redis, QUEUE_CONNECTION=redis, SANCTUM_STATEFUL_DOMAINS, SESSION_DOMAIN.

- Secrets: never in Git, DB, logs, or client bundle (NFR-SEC-005); dev uses weak defaults, production uses a secrets manager and a least-privilege DB role (docs/ENVIRONMENT.md security notes). APP_KEY generated per environment.

- Dependency management: lockfiles committed; Composer/npm versions pinned; images pinned by tag (pgvector/pgvector:pg17, redis:7-alpine, nginx:1.27-alpine, php:8.4-fpm).

- Database schema: the only mechanism for schema change is a migration; schema changes are change-controlled (CON-02, §25) and verified via migrate:fresh→rollback→migrate.

- Infrastructure as code: compose.yaml + docker/*/Dockerfile (multi-stage: development/production) are versioned artifacts.

- Configuration items baselined: SRS, SDD, SPMP, schema (DBML + migrations), CI config, Docker/infra, API contract.

## 21. Release Management

- Versioning: Semantic Versioning MAJOR.MINOR.PATCH. Phase GAs are minor/major releases (e.g. P2 GA = v1.0.0, P3 = v1.1.0, P4 = v1.2.0); fixes are patches.

- Release train: feature-complete → freeze (optional release/*) → hardening (security/a11y/perf/UAT) → tag → deploy to staging → client sign-off → promote to production.

- Changelog: generated from Conventional Commits per release.

- Build artifacts: production Docker image (baked source + composer install --no-dev --optimize-autoloader) and the built SPA (vite build) served as static assets by Nginx (no dev Vite/node in prod) (SDD §5.2, §9.1).

- Feature toggles: incomplete or opt-in features gated by settings (ai_system_settings, system_settings) rather than code branches — e.g. AI predictions ship off (CON-07).

- Rollback: redeploy the previous tagged image; restore the database from the pre-deploy backup if a migration must be reverted (§27).

Release and rollback tooling — implemented by WP-2.7d, and what its status actually is (recorded 2026-09-06).

The strategy above is now backed by scripts rather than by procedure alone (SDD DD-64):

Table …. Release Management

| Script | What it does |
| --- | --- |
| scripts/deploy-prod.sh | Builds, tags the immutable sccit/{app,web}:prod-<sha> images, takes a pre-deploy database snapshot, and writes releases/<sha>/manifest.json |
| scripts/releases.sh | Lists retained releases and the images and snapshot each one names |
| scripts/rollback-prod.sh | Restores a named release by re-tagging its images; refuses an unknown release with a non-zero exit and the live image verifiably unchanged |
| scripts/backup.sh / restore.sh | Database snapshot and restore, used by the two above and independently |

Rolling back by rebuilding is not a rollback — it rebuilds whatever the branch says now, which is the state being escaped. Immutable per-commit tags make “the image that was running” a nameable object, and the manifest is what ties it to a database snapshot.

The distinction that must not be blurred:

- Rollback tooling is implemented and verified to fail safe. An unknown release exits 1 at the first stage with sccit/app:prod unchanged; no argument exits 2.

- A real production rollback has never been exercised. No deployment has been authorized, so releases/ is absent and no prod-<sha> tag exists. The end-to-end path is unproven and is a deployment-time verification item, not a delivered guarantee.

- The surviving sccit/{app,web}:rollback-preWP26b images predate this convention — no prod-<sha> naming, no manifest — so the new tooling cannot use them. Until the first tracked deployment exists they are the only rollback path there is, and it is the manual WP-2.6b one. Keep them until then.

Full production rollback proof requires two tracked deployments and a controlled window in which a retained release is actually restored.

## 22. Risk Management

Product/technical risks are inherited from SRS §32 RSK-01..10 (AI provider, PII-to-AI, counter-cache drift, scope creep, a11y regressions, perf at volume, aging hardware, open-decision ambiguity, backup untested, single-tenant assumption). This section adds project/management risks and the control process.

Table …. Risk Management

| ID | Project risk | L | I | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| PR-01 | Team capacity/velocity unconfirmed → schedule uncertainty. | H | M | Relative sizing; confirm capacity at approval; re-baseline after 2 sprints of actuals (SA-01/03). | R-PM |
| PR-02 | Bus factor (small team / single contributor). | M | H | ADRs + Claude-Mem + vault docs; pairing; ≥ 1 reviewer per PR; automated everything. | R-DEV |
| PR-03 | Client-gate availability delays phase starts. | M | M | Schedule gate reviews in advance; keep decisions batched; async approval option. | R-PM |
| PR-04 | AI provider cost/latency/policy change (P3). | M | M | Provider abstraction (SDD DD-11); token/latency logging; degrade gracefully; cost budget alert. | R-DEV |
| PR-05 | Third-party dependency churn (React 19 / Tailwind 4 / Laravel 13 ecosystem). | M | M | Pinned lockfiles; scheduled update sprints; CI catches breakage. | R-DEV |
| PR-06 | Scope creep from Future/opt-in features into P2. | M | M | Firm phasing; §25; Future items stay in §32. | R-PM |
| PR-07 | Open decisions (SRS OI-01..11) unresolved before their phase. OI-08..11 were resolved on 2026-08-28, clearing the decision gate for WP-2.6b; OI-01, OI-03..07 remain open against their own phases. | M | M | Track as change items; force resolution at the relevant gate. | R-PM |
| PR-08 | Environment drift (dev vs prod) causes “works on my machine”. | L | M | Docker parity; identical CI DB; staging mirrors prod. | R-DEV |

Process: risk register reviewed every sprint; each risk has L (likelihood), I (impact), mitigation, and owner; new risks logged in Issue Management with a risk label; top risks reported at each gate.

## 23. Issue Management

- Tracker: GitHub Issues (SA-05), linked to PRs and commits (Conventional Commit footers / “Closes #”).

- Types/labels: bug, feature, tech-debt, security, a11y, performance, risk, docs, question; phase labels P2/P3/P4.

- Severity (defects): S1 blocker (prod down / data loss) · S2 major (feature broken, no workaround) · S3 minor (workaround exists) · S4 cosmetic.

- Triage: new issues triaged within one working day; S1/S2 interrupt the sprint; S3/S4 enter the backlog.

- Traceability: every issue references the SRS/SDD ID(s) it affects; every fix references its issue and adds a regression test.

- Definition of resolved: fix merged (CI green), regression test added, verified against acceptance, closed with a note.

## 24. Communication Plan

Table …. Communication Plan

| Event | Frequency | Participants | Output |
| --- | --- | --- | --- |
| Async daily status | daily | team | short written update (blockers). |
| Sprint planning | per sprint | team (+PO) | committed sprint backlog. |
| Sprint review/demo | per sprint | team + PO | demo of vertical slices vs acceptance. |
| Sprint retrospective | per sprint | team | process improvements. |
| Phase-gate review | per phase (M0,M5,M6,M7) | team + client | acceptance sign-off / go-no-go. |
| Risk review | per sprint | team | updated risk register. |
| Ad-hoc decision record | as needed | R-DEV | ADR in vault/08 ADR. |

Channels: repository (issues/PRs) is the system of record; synchronous calls for gate reviews; decisions captured as ADRs (structure) + Claude-Mem (rationale). Reporting: a one-page status per sprint (progress vs milestones, risks, defects, next gate).

## 25. Change Management

- Baselines under change control: the SRS, SDD, and SPMP; the database schema; the API contract.

- Change request (CR) flow: raise CR (issue, change label) → impact analysis against SRS/SDD/schedule/cost → decision (R-DEV + R-PM, client for scope/cost) → update the affected baselined document with a version bump → implement.

- Schema changes additionally require a migration + review and a migrate:fresh→rollback→migrate verification (CON-02, §20).

- The open product decisions (SRS OI-01..11) are pre-registered change items: single vs multi-role, self-registration (resolved), MFA, QR expiry, SLA model, auto-escalation, confirm NFR targets, and — added with the QR workflow clarification — the QR scan entry surface, where technician support requests live, face-to-face scheduling depth, and the request status vocabulary. Each must be resolved before the phase it affects. Resolution is recorded in place against Version 1.0, per the client’s instruction that the document version label is not to be advanced, and cascades to the SDD/SPMP as needed.

- Document versioning: SemVer-style for docs (1.0 → 1.1); revision history table in each document; superseded versions retained.

- No silent scope change: anything outside the SRS scope is a CR, not a task.

## 26. Deployment Strategy

Architecture references: SDD §5 (Deployment) and SDD §37 (Deployment diagrams).

- Environments: development (Docker on workstation) → staging (production-like, used for UAT and release validation) → production.

- Production shape: TLS-terminating edge; stateless Laravel app containers scaled horizontally behind it; the SPA served as a static build; Redis for cache/session/queue; separate queue and scheduler workers; managed/backed-up PostgreSQL (SDD §5.2, SDD §9.1).

- Release procedure: build tagged image + SPA → deploy to staging → run migrations → smoke + acceptance on staging → client sign-off → promote to production (rolling/blue-green on the stateless tier for near-zero downtime) → run migrations → post-deploy health check (/up, /api/health).

- Database migrations: forward-only in production; destructive changes gated by a pre-deploy backup and a rollback plan.

- Config/secrets: injected via environment/secrets manager; SANCTUM_STATEFUL_DOMAINS/SESSION_DOMAIN set to the production origin.

- Rollback: previous image + (if needed) DB restore (§27).

- [SA-06] The concrete production hosting target (managed containers vs VM, managed Postgres vs self-hosted) is confirmed with the client before M5; the design is host-agnostic.

## 27. Backup and Recovery Strategy

Realizes SRS NFR-AVL-003/004.

- Backups: PostgreSQL dumps via the existing scripts/backup.sh (pg_dump | gzip → backups/<db>-<ts>.sql.gz); in production, scheduled (cron/scheduler) and shipped off-site, with WAL/PITR enabled where the hosting supports it.

- Targets: RPO ≤ 24 h (target ≤ 1 h with PITR); RTO ≤ 4 h.

- Restore: scripts/restore.sh (make restore FILE=…); a documented restore drill is performed before M5 and periodically thereafter (NFR-AVL-004) — an unrehearsed backup is treated as no backup (RSK-09).

- Retention: backups retained per policy; PII and high-volume logs pruned per NFR-SEC-015 while honoring legal holds.

- Backup inventory: the backup_history table records backup runs (type/status/location/size) for auditability.

- File assets: attachment/repair-image storage included in the backup scope (stored outside the web root, NFR-SEC-007).

## 28. Monitoring Strategy

Realizes SRS NFR-OBS-* and NFR-AVL-001.

- Health: framework /up and /api/health (DB + Redis reachability) feed orchestrator liveness/readiness and uptime monitoring (SDD §5.2).

- Structured logs with per-request correlation ids propagated to jobs and provider calls (SDD §20); shipped to a log aggregator in production.

- Metrics: request latency (vs SRS §13 p95 targets), error rate, queue depth/failure rate, DB connections; AI token/latency captured on analysis/conversation rows (NFR-OBS-003).

- Alerting: on health failure, error-rate spikes, queue backlog, failed backups, SLA-breach volume, and (P3) AI cost/latency thresholds.

- Availability: measured against ≥ 99.5% business-hours target (NFR-AVL-001); planned downtime scheduled via maintenance_windows and announced.

- Security events: login/lockout/permission-change and audit-trail volume monitored (§29).

## 29. Security Management

Design references: SDD §29 (Security Architecture) implementing SRS §12.

- Ownership: R-DEV owns security posture; security is a release gate each phase (DL-09).

- Secrets: managed via a secrets manager in production; least-privilege DB role (not the dev superuser); never committed (docs/ENVIRONMENT.md).

- Dependency & code security: dependency vulnerability scanning in CI; the repo’s security-review tooling run on security-sensitive PRs; static analysis (Larastan) enforced.

- Application controls (verified per phase): uuid-only external ids, deny-by-default RBAC, Sanctum first-party cookies + CSRF, server-side validation, output encoding, file-upload allow-list + checksum, append-only audit, rate limiting (SRS NFR-SEC-001..017).

- AI data governance (P3): data minimization/redaction before any Gemini call; AI advisory-only; transparency and disable switch (SRS §17.5, RSK-02).

- Access control (project): production access least-privilege; audit of privileged actions (NFR-SEC-017).

- Incident response: severity-based (align to issue severities); S1 security incident → contain, assess, notify stakeholders, remediate, post-mortem + ADR.

- Reviews: a full security review precedes each phase GA; findings tracked as security issues and closed before release.

## 30. Acceptance Process

- Basis: the acceptance criteria in SRS §31 — the six global gates AC-G1..G6 plus per-feature criteria (AC-TKT-*, AC-AI-*, etc.).

- Per work item: demonstrated against its acceptance criteria at sprint review (Definition of Done).

- Per phase (formal): an acceptance package is prepared for the phase-gate review — passing CI, coverage report, security review report, WCAG 2.2 AA audit report, load-test results, and UAT results against the operational scenarios (SRS §26).

- UAT: client-side users execute scripted scenarios on staging; defects triaged by severity; S1/S2 must be resolved before sign-off.

- Sign-off: the client formally approves the phase gate (M5/M6/M7); approval authorizes production release and the start of the next phase.

- Definition of acceptance: all mandatory (M) requirements for the phase pass; Future items are explicitly excluded and remain in the roadmap.

## 31. Maintenance Plan

Post-GA steady state (begins at M5, formalized at M8):

- Support model: issue-tracker intake with the severity SLAs; S1 hotfix path via hotfix/* → tag → deploy.

- Corrective: bug fixes with regression tests; adaptive: dependency/security updates on a scheduled cadence (e.g. monthly), each through CI; perfective: performance/UX improvements from monitoring and feedback; preventive: tech-debt sprints, backup restore drills, log/PII retention pruning (NFR-SEC-015).

- Operational routines: verify backups + periodic restore drill (NFR-AVL-004); review audit/security logs; watch SLA-breach and AI-cost trends.

- Knowledge continuity: ADRs and Claude-Mem kept current; onboarding doc maintained; the vault is the durable engineering record.

- Handover pack (DL-13): runbooks (deploy, rollback, backup/restore, incident), environment/secret inventory (names only), monitoring/alert catalog, and the current documentation set.

## 32. Future Roadmap

Beyond the committed phases; scope-controlled and not part of P2–P4 unless promoted via §25. Sources: SRS §34 and SDD §38 EXT-01..11.

Table …. Future Roadmap

| Horizon | Item | Reference |
| --- | --- | --- |
| Near | Resolve open decisions that add capability (MFA, multi-role, SLA policies, auto-escalation). | SRS OI-01..07, EXT-04/05 |
| Near | Saved/scheduled reports + analytics materialized views. | FR-RPT-006/007, EXT-03 |
| Mid | Predictive maintenance enabled at scale (currently opt-in, default off). | FR-AI-011/012, EXT-02 |
| Mid | Log partitioning + read replica as volume grows. | NFR-SCAL-004/007, EXT-08 |
| Mid | Additional UI locales (strings already externalized). | NFR-I18N-002, EXT-09 |
| Long | Network topology / heat maps (optional PostGIS). | SRS §19 (future), EXT-07 |
| Long | Programmatic API tokens for integrations. | EXT-06 |
| Long | Multi-tenancy (would require a tenancy/RLS re-architecture — flagged, not seamed). | CON-08, EXT-11 |

## Appendix A — Tooling & Command Reference

From the implemented repo (Makefile, scripts/, .github/workflows/ci.yml, docs/DEVELOPMENT.md):

Table …. Appendix A — Tooling & Command Reference

| Task | Command |
| --- | --- |
| Start / stop stack | make up / make down |
| Logs / status | make logs / make ps |
| Shell in app container | make shell |
| Migrate / fresh | make migrate / make fresh |
| Lint (all) | make lint (Pint --test + Larastan + ESLint) |
| Format (all) | make format (Pint + Prettier) |
| Test (all) | make test (Pest + Vitest) |
| DB backup / restore | make backup / make restore FILE=… |
| psql / redis shell | make psql / make redis |
| CI (auto) | .github/workflows/ci.yml — backend + frontend jobs on push/PR to main |

CI gates enforced: backend — Pint --test, Larastan (L6, --memory-limit=512M), Pest (against pgvector/pgvector:pg17 service DB); frontend — ESLint, Prettier --check, Vitest, vite build (Node 22).

## Appendix B — Assumption Register

All calendar/resourcing figures are assumptions pending confirmation at plan approval.

Table …. Appendix B — Assumption Register

| ID | Assumption | Impact if wrong | Confirm by |
| --- | --- | --- | --- |
| SA-01 | Team capacity supports the indicative durations in §11; schedule is re-baselined after 2 sprints of actual velocity. | Timeline shifts (not scope). | Plan approval |
| SA-02 | Small team; roles (§7) may be held by few people; AI assistance is human-reviewed. | Role coverage / bus-factor (PR-02). | Plan approval |
| SA-03 | Sprint length = 2 weeks. | Cadence of reviews/gates. | Plan approval |
| SA-04 | main branch protection with required PR + green CI is enabled. | Quality-gate enforcement. | Before P2 |
| SA-05 | Issue tracking uses GitHub Issues (same platform as CI). | Tooling for §23. | Plan approval |
| SA-06 | Production hosting target chosen before M5; design is host-agnostic. | Deployment specifics (§26). | Before M5 |
| SA-07 | Client provides UAT participants and timely gate approvals. | Gate scheduling (PR-03). | Per phase |
| SA-08 | Production secrets manager + least-privilege DB role available in prod. | Security posture (§29). | Before M5 |
| SA-09 | A Gemini API key with adequate quota/budget is provided for P3. | P3 start (RSK-01/PR-04). | Before P3 |

## Appendix C — Consistency Review Log

Per the required post-generation review: verify consistency with the SRS and SDD, remove contradictions/duplication, and improve clarity.

### C.1 Sources reconciled

SRS v1.0 (phasing, FR/NFR/BO/RSK/CON/ASM/OI IDs, acceptance §31); SDD v1.0 (domains, DD-01..16, RES-01/02, deployment §5/§37, tech stack); and the current repository — .github/workflows/ci.yml, Makefile, scripts/*, docs/DEVELOPMENT.md, docs/ENVIRONMENT.md, scripts/backup.sh, compose.yaml — read directly for realism.

### C.2 SRS/SDD consistency — confirmed

- Phasing (P2/P3/P4/Future) is identical across SRS, SDD, and this plan; the WBS, phase plan, milestones, and roadmap all use it.

- Acceptance references SRS §31 (global gates + feature ACs) rather than inventing new criteria.

- Domains in the WBS match SDD §14, including the two new P2 domains from RES-01 (Locations) and RES-02 (Identity, Administration) — the plan schedules exactly those.

- Risks: product/technical risks are inherited from SRS §32 (RSK-*) and not duplicated; only project/management risks (PR-*) are added here.

- Open decisions (OI-01..11) are carried as change items in §25/§32, consistent with the SRS. OI-08..11 were added with the QR workflow clarification and resolved by the Client on 2026-08-28, recorded in place against Version 1.0.

- Security/backup/deployment reference SDD §29/§5/§37 and SRS NFR targets (RPO ≤ 24 h, RTO ≤ 4 h, uptime ≥ 99.5%) without restating them.

### C.3 Repository consistency — confirmed

CI gates, make/scripts commands, env-file strategy, Redis-for-everything scale-readiness, Sanctum stateful-domain config, and the backup.sh/restore.sh flow described here match the implemented files exactly (Appendix A). The baseline underlying this plan matches the git history (phases 0–7 + DB layer) and the SDD’s statement that the application layer is not yet built.

### C.4 Contradictions & duplication removed

- No duplication of requirements/design/schema: all referenced by ID; product scope defers to SRS §3; deployment/security defer to SDD.

- Risk duplication avoided: SRS RSK-* referenced, not copied; management risks separated as PR-*.

- Single phasing vocabulary: eliminated any ambiguity between “Phase 2 (business logic)” and SRS “P2” by treating them as the same thing (P2 = the first application build phase after documentation).

- Assumptions consolidated in Appendix B and cross-referenced from the body, rather than scattered.

### C.5 Clarity & maintainability improvements

Milestones are acceptance-defined (robust to schedule change); calendar figures are explicitly assumptions; the plan references living artifacts (CI, Makefile, docs) so it stays true as the repo evolves; every section ties to an owner and, where relevant, an SRS/SDD ID.

### C.6 Residual items

None blocking. Confirm the Appendix B assumptions (chiefly team capacity SA-01/02/03) at plan approval to finalize the indicative schedule; resolve SRS OI-01..07 before their respective phases. No contradictions with the SRS or SDD remain.

End of Software Project Management Plan v1.0 — Version 1.0 baseline — Waiting for Client Approval. Phase 2 development proceeds on separate go-ahead.