"ACTION — PHASE 2.8 FLOOR PLAN RECONNAISSANCE REPORT"

Project:  "SccIT — School IT Service Management System"

Date:  "2026-09-27"

Author:  "Engineering"

Status:  "Read-only — no code, schema, migrations, tests, config, Docker, docs, database or Git state was modified"

## 1. Executive summary

The Interactive Floor Plan is the most thoroughly pre-specified feature in this project. It was designed at bootstrap, baselined into all three controlled documents, given a database schema that has been migrated since day one, given seeded permissions and settings, given a sequence diagram, given a status enum written specifically for it — and it is already publicly promised on the shipped marketing site.

What does not exist is any of its code. The FloorPlan domain holds 0 PHP files and 13 `.gitkeep` placeholders. There are zero floor-plan tests. Laravel Reverb is not installed in any form.

Phase 2.8 is therefore best understood as wiring up existing preparation, not greenfield design. The requirements do not need to be invented; they need to be recovered, and this report recovers them.

Headline recommendation. Deliver a genuinely interactive, persistent, accessible, admin-only floor plan for the presentation using SVG rendering + a polling synchronisation channel, and stage Laravel Reverb as a post-presentation upgrade. Polling is not a shortcut invented here: SDD DD-16 already specifies "Reverb for real-time (P4) *with polling fallback* … degrade gracefully." This satisfies the observable behaviour of FR-FP-007 while avoiding four coupled infrastructure changes four days before a client presentation.

| Question | Finding |
| --- | --- |
| Is the data model sufficient? | Yes, completely. No schema change is required for the core feature. |
| Is the authorization model ready? | Yes. floorplan.view / floorplan.manage are seeded and live. |
| Is Reverb ready? | No. It does not exist — no package, no config, no channels, no client. |
| Is real-time therefore blocked? | No. DD-16 approves a polling fallback. |
| Is there frontend preparation? | Yes — a working static FloorPlanVisual.tsx and a reserved feature seam. |
| Is there demo data? | Yes — 4 layouts and 20 positions are already in the dev database. |
| Largest schedule risk | Reverb's deployment surface, and the production image predating Phase 2.7. |
| Largest specification conflict | Admin-only. The original client brief says admin-only; the SRS grants technicians `floorplan.view`, and they hold it today. |

## 2. Existing Phase 2.8 preparation discovered

### 2.1 Database — complete, migrated, and already populated

backend/database/migrations/2026_06_30_100020_create_location_tables.php:73-105

room_layouts          id, room_id, version (default 1), width, height,
                      grid_size (default 20), background_image, is_active,
                      created_by, updated_by, timestampsTz
                      UNIQUE (room_id, version)
                      CHECK width > 0 AND height > 0 AND grid_size > 0

floor_plan_positions  id, room_layout_id, pc_unit_id,
                      pos_x decimal(10,2), pos_y decimal(10,2),
                      rotation decimal(5,2) default 0, z_index int default 0
                      UNIQUE (room_layout_id, pc_unit_id)
                      CHECK pos_x >= 0 AND pos_y >= 0

Plus the partial unique index enforcing one active layout per room (2026_06_30_100100_create_advanced_db_objects.php:49):

CREATE UNIQUE INDEX room_layouts_one_active_per_room ON room_layouts (room_id) WHERE is_active;

Foreign keys cascade from rooms and pc_units (2026_06_30_100090_add_foreign_keys.php:46-50).

Live development database, queried read-only during this reconnaissance:

| Table | Rows |
| --- | --- |
| buildings | 4 |
| floors | 6 |
| rooms | 13 |
| pc_units | 24 |
| room_layouts | 4 |
| floor_plan_positions | 20 |

The feature is demonstrable against existing data on day one.

### 2.2 Why the schema looks like this — the recovered design history

docs/database/database_architecture_report.md:47, decision D3:

Generalize locations: laboratories → rooms (with room_type); new floors

between buildings and rooms; laboratory_layouts → room_layouts (+ grid_size,

version, is_active); **positions moved off pc_units into

floor_plan_positions (layout-scoped)** … makes the Interactive Floor Plan

addable "without major refactoring."

The original review finding (docs/database/database_design_review.md:163, M4) explains why positions are layout-scoped: "Position currently lives on `pc_units.pos_x/pos_y`, which breaks when a PC moves between rooms or when a room has multiple/versioned layouts." That is FR-FP-008 solved in the schema.

A recommended constraint that was deliberately not implemented (docs/database/database_design_review.md:268-269):

Coordinates within layout bounds: pos_x BETWEEN 0 AND layout.width (app-level if

cross-table), pos_y BETWEEN 0 AND layout.height.

The shipped database enforces only >= 0. Upper-bound containment is therefore application-layer work that Phase 2.8 must do — a recovered requirement, not a new proposal.

### 2.3 Models — present but bare

| File | State |
| --- | --- |
| backend/app/Models/RoomLayout.php | room(), positions(), is_active cast |
| backend/app/Models/FloorPlanPosition.php | layout(), pcUnit(), decimal casts |
| backend/app/Models/Room.php | already has layouts(): HasMany<RoomLayout> |
| backend/app/Models/PcUnit.php | already has positions(): HasMany<FloorPlanPosition> |

Gap: neither RoomLayout nor FloorPlanPosition has a uuid column, HasUuidRouteKey, or soft deletes — unlike every other publicly addressable entity (SDD DD-06). The project rule is that numeric ids are never addressable (NFR-SEC-001, AC-G2).

### 2.4 Permissions — seeded, live, and already consumed

backend/database/seeders/PermissionSeeder.php:30 → 'floorplan' => ['view','manage']

Verified against the running development database:

| Role | Floor-plan grants |
| --- | --- |
| administrator | floorplan.view, floorplan.manage |
| technician | `floorplan.view` |
| teacher | (none) |

floorplan.view is already an accepted consumer permission inside RoomPolicy::LOCATION_CONSUMERS (:50) and PcUnitPolicy::PC_CONSUMERS (:41), so a holder can already resolve rooms and PC units through /api/lookups/*.

### 2.5 Settings — seeded

backend/database/seeders/SystemSettingSeeder.php:42-43, both is_public = true:

['floor_plan', 'floor_plan.default_grid_size', 'Floor Plan Grid Size (px)', 20, 'integer', true, false],
['floor_plan', 'floor_plan.snap_to_grid',      'Snap To Grid',            true, 'boolean', true, false],

However there is no `SystemSettingService`. Runtime reads are ad-hoc private helper methods duplicated across QrService, TicketLifecycle and MaintenanceMetrics. There is no caching and no HTTP surface.

### 2.6 The P4 sequence diagram — it exists

| Artifact | Status |
| --- | --- |
| docs/diagrams/source/sdd-07-real-time-floor-plan-update-p4.mmd | Exists, 11 lines |
| docs/diagrams/sdd-07-real-time-floor-plan-update-p4.svg | Exists, 26,487 bytes |
| docs/diagrams/sdd-07-real-time-floor-plan-update-p4.png | Exists, 62,745 bytes |
| Embedded in SDD §35.7 | Yes, line 1077-1090 |

Admin SPA  ->> AssetPositionService : PATCH position (snap-to-grid)
           ->> PostgreSQL           : upsert floor_plan_positions (unique layout+pc)
           ->> Reverb               : broadcast PositionUpdated
Reverb    -->> Viewer SPA           : event (or polling fallback)
Viewer SPA ->> itself               : re-render PC icon at new pos/status

It specifies PATCH, snapping applied before persistence, an upsert, and explicitly tolerates "or polling fallback".

Other floor-plan-bearing diagrams: sdd-09-backend-domain-components.mmd:10 (FloorPlan --> Locations), activity-admin.mmd:40, use-case-diagram.puml:66 (UC26 "Manage Floor Plan"), and the Reverb node RVB[Reverb P4] in sdd-08-system-components.mmd. No editor mockup or UI wireframe exists.

### 2.7 Status model — written for this feature

backend/app/Enums/PcStatus.php, docblock verbatim:

PC operational status. Values align to the Interactive Floor Plan icon colors.**

Cases: available, assigned, online, offline, under_maintenance, retired — exactly the six FR-FP-004 enumerates.

It has no `label()` or `tone()` override, unlike AssetStatus, which established the project convention that the server returns the tone so the client never hard-codes a status colour. Adding those two helpers is the one enum change the feature needs.

### 2.8 Frontend — a reserved seam and a working prototype

`frontend/src/components/marketing/visuals/FloorPlanVisual.tsx` — a real,

shipped, static rendering of this exact UI, already citing FR-FP-004: CSS linear-gradient grid background at 28px, absolutely-positioned percentage nodes, Monitor lucide icon, status tone map, selected ring + tooltip, StatusPill legend, wrapped in <figure role="img" aria-label="…">. This is the visual language to inherit.

frontend/src/features/floor-plan/README.md — the reserved seam; prescribes

consuming the API via src/services/api.ts and keeping "heavy canvas state … in a feature-local Zustand store under `features/floor-plan/stores`".

frontend/src/components/ui/StatusPill.tsx — *"The one status vocabulary shared

across tickets, assets, maintenance, and the floor plan"*; subtle wash + strong same-hue text + leading dot, never colour-only.

.impeccable/design.json / DESIGN.md:327 — the Flat-Plane Rule explicitly

sanctions a shadow on a drag preview; a documented "Do" reads "pair every status colour with a text label and shape/icon"; the One Voice Rule caps Signal Blue at ≤10% of any screen.

### 2.9 Navigation — already built

GET /admin/locations/tree (LocationTreeController) returns buildings → floors with per-level counts; rooms are fetched per floor via GET /admin/rooms?floor=<uuid>, deliberately, "so the tree payload stays bounded regardless of estate size".

The school → building → floor → room navigator the brief asks for already exists.

### 2.10 Audit — the history mechanism already exists

AuditLogger::activity(action, actor, subject, properties, request, module, description) writes activity_logs (337 rows live) with a subject morph and a jsonb properties bag.

audit_logs exists but is unwired and empty (0 rows) — the SDD's "Auditable observer" is design intent, not code. Use `activity_logs`.

Critically, the project has a documented precedent for exactly the question Phase 2.8 asks. SDD DD-55: there is deliberately no `statushistory table — the activity rows, written in the same transaction with before/after values in properties`, are the history. Applied here, position history needs no new table*.

### 2.11 Public marketing copy already promises this feature

frontend/src/components/marketing/FloorPlanSection.tsx is live on the landing page and constitutes a de-facto commitment:

"See the whole floor, not just a list." … *"Drag-and-drop, snap-to-grid

positioning of every PC on per-room canvases, versioned over time."* …

*"Icons colored by the universal status palette — with a shape and label so meaning

survives color-blindness." … "Position and status changes reflect to other viewers

in real time over Laravel Reverb." … "A keyboard, non-drag alternative for

placement keeps the whole map operable without a mouse."*

This matters for the presentation: the site names Reverb explicitly. If Phase 2.8 ships with polling, either the copy is adjusted or the claim is knowingly ahead of the build. Flagged as OWNER DECISION D8.

## 3. Exact files, classes, tables, routes and components found

| Kind | Artifact | State |
| --- | --- | --- |
| Tables | room_layouts, floor_plan_positions | Migrated, populated |
| Index | room_layouts_one_active_per_room | Exists (partial unique) |
| CHECKs | room_layouts_dimensions_check, floor_plan_positions_coords_check | Exist |
| Models | RoomLayout, FloorPlanPosition | Exist, bare (no uuid) |
| Relations | Room::layouts(), PcUnit::positions() | Exist |
| Factories | RoomLayoutFactory, FloorPlanPositionFactory | Exist |
| Seeders | DemoSeeder (lines 66-93), SystemSettingSeeder:42-43, PermissionSeeder:30,75 | Exist |
| Enum | PcStatus (6 cases) | Exists; no label()/tone() |
| Permissions | floorplan.view, floorplan.manage | Seeded and granted |
| Domain | backend/app/Domains/FloorPlan/ | 0 PHP files, 13 `.gitkeep`, 1 README |
| Frontend seam | frontend/src/features/floor-plan/ | README only |
| Prototype | FloorPlanVisual.tsx, FloorPlanSection.tsx | Exist, shipped (marketing) |
| Diagram | sdd-07-…-p4 .mmd / .svg / .png | Exist |
| Requirements | FR-FP-001..010, NFR-ACC-008, AC-FP-003, UC-12/UC26 | Baselined |
| Architecture | SDD §25, §35.7, DD-16, RES-01, EXT-01 | Baselined |
| Work packages | SPMP WP-4.1, WP-4.2, WP-4.3, milestone M7 | Baselined |
| Routes | None | — |
| Controllers / Services / Policies / Requests / Resources | None | — |
| Tests | None — zero references to RoomLayout or FloorPlanPosition | — |
| TypeScript types / hooks / components | None | — |

### 3.1 Demo seed detail

backend/database/seeders/DemoSeeder.php:66-93 creates 1 building × 2 floors × 2 laboratory rooms, each with 1 active layout and 5 positioned PCs:

'pos_x' => ($index % 5) * 120 + 40,
'pos_y' => intdiv($index, 5) * 120 + 40,

Net effect: all five PCs in a single row at y = 40, x = 40/160/280/400/520, inside layouts 800–1920 × 600–1080. The second building and the workshop floor get no layouts at all. The data is present but visually thin — worth improving for a demonstration.

## 4. Verified-absent — what does NOT exist

Each of these was checked directly, not assumed.

| Expected | Reality |
| --- | --- |
| laravel/reverb | Absent from backend/composer.json |
| backend/config/broadcasting.php | Does not exist |
| backend/routes/channels.php | Does not exist |
| Any ShouldBroadcast event | Zero across backend/app/ (11 domain events, none broadcast) |
| laravel-echo / pusher-js | Absent from frontend/package.json |
| BROADCAST_CONNECTION | null; every REVERB_* key is commented out |
| Drag library (dnd-kit, react-dnd) | None installed |
| Canvas library (konva, react-flow, d3) | None installed |
| Virtualization | None installed |
| Floor-plan tests | Zero |
| Floor-plan planning artifacts in .claude/ | None |
| Floor-plan commits in Git history | None (git log --all -i --grep="2.8" → empty) |
| Floor-plan material in recovery/forensic archives | None |

Two stale repository notes to correct at phase close. The FloorPlan README

claims "Broadcasting config + env placeholders are already in place" — only the

env comment exists. It also lists BuildingService/FloorService as FloorPlan

services, which RES-01 superseded by moving them to Locations.

### 4.1 Reverb's true deployment surface

Enabling Reverb is not composer require. It touches four coupled surfaces:

A new container service in both compose.yaml and compose.prod.yaml.

nginx WebSocket proxying. Dev nginx proxies Upgrade/Connection **only for

the Vite HMR socket (`docker/nginx/default.conf:54-65`). `docker/nginx/prod.conf` has no WebSocket handling at all**.

The production CSP. docker/nginx/security-headers.prod.conf is

connect-src 'self', with the inline comment "there is no HMR socket here". It is covered by a regression test, backend/tests/Feature/Security/ContentSecurityPolicyTest.php, which would have to change with it.

A production image rebuild — code plus config/route/event caches are baked in.

This buys exactly one requirement, FR-FP-007, which DD-16 already permits satisfying by polling.

(Note: the commented placeholder `REVERB_PORT=8080` collides with the dev application port and is unusable as written.)

## 5. Numbering and scheduling — the critical correction

"Phase 2.8" is conversational numbering. It is not SPMP `WP-2.8`.

SPMP WP-2.8 = "Administration pt.2: system settings + branding" (FR-CFG-*),

docs/Software Project Management Plan.md:256.

The floor plan is SPMP `WP-4.1` / `WP-4.2` / `WP-4.3` under Release P4

(:345-347), gated by milestone M7 (:385).

| WP-4.1 | Reverb + broadcasting infrastructure                       | FR-FP-007, FR-NOT-007        | M | P2 GA            |
| WP-4.2 | Floor-plan editor: layouts, drag/snap positions, keyboard alt | FR-FP-001/003/009         | L | WP-4.1, WP-2.2/2.3 |
| WP-4.3 | Live status/position + info panels; P4 hardening + GA      | FR-FP-002/004/005/007/008    | L | WP-4.2           |

### 5.1 The documented dependency that Phase 2.8 breaks

`WP-4.1` depends on "P2 GA", and P2 GA (milestone M5) requires:

*SRS §31 AC-G1..G6 pass; security review + WCAG AA audit + load test pass; UAT

sign-off; deployed to production.*

Outstanding P2 packages: WP-2.4b, WP-2.8, WP-2.9, WP-2.10, WP-2.11. Release P3 (AI & Knowledge Base) is also scheduled ahead of P4.

Proceeding with Phase 2.8 now means consciously advancing P4 ahead of remaining P2 and all of P3, against a recorded dependency. That is a legitimate client choice driven by demonstration value, but it must be recorded as a decision rather than absorbed silently. See OWNER DECISION D1.

Note also the ordering within P4: the SPMP puts Reverb first (WP-4.1), because WP-4.2 depends on it. This report recommends inverting that order — build the editor against a polling channel, add Reverb after — which is itself a departure to be recorded.

## 6. Previously documented requirements — recovered verbatim

### 6.1 SRS §19, FR-FP-001..010

| ID | Requirement (the system shall …) | Class | Rel |
| --- | --- | --- | --- |
| FR-FP-001 | Allow Administrators to create per-room layouts with canvas width/height (>0) and grid size (>0, default 20 px), an optional background image, versioning, and at most one active layout per room. | M | P4 |
| FR-FP-002 | Render an interactive canvas showing PC units positioned within the active room layout, with pan and zoom. | M | P4 |
| FR-FP-003 | Allow Administrators to place, drag-and-drop, snap-to-grid, rotate, and layer (`z_index`) PC icons, persisting positions to floor_plan_positions (unique per layout+PC; coordinates ≥ 0). | M | P4 |
| FR-FP-004 | Colour PC icons by status (available/assigned/online/offline/under_maintenance/retired) using the universal status palette, with a text/shape label so meaning survives colour-blindness. | M | P4 |
| FR-FP-005 | Open a click-through info panel for a PC showing specs, installed hardware, QR, ticket history, maintenance timeline, and (if enabled) AI predictions. | M | P4 |
| FR-FP-006 | Restrict layout editing to Administrators (floorplan.manage); Technicians/others may view (floorplan.view). | M | P4 |
| FR-FP-007 | Reflect PC position and status changes to other viewers in real time via Laravel Reverb. | M | P4 |
| FR-FP-008 | Preserve position history across layout versions and support a PC moving between rooms without data loss. | M | P4 |
| FR-FP-009 | Meet accessibility requirements for drag interactions, providing a keyboard/non-drag alternative for placement. | M | P4 |
| FR-FP-010 | Network-topology visualization, heat maps, asset-density overlays, AI-predicted failures on the map, indoor navigation. | F | — |

`NFR-ACC-008` (SRS:741): "Ensure target sizes and drag interactions (incl. the future floor plan) meet WCAG 2.2 target-size and dragging-movement criteria, providing a non-drag alternative."

`AC-FP-003` (SRS:1538) — the only floor-plan acceptance criterion: "Given an active room layout, when an admin drags a PC and saves, then the snapped position persists to `floor_plan_positions` and is broadcast to other viewers; a keyboard alternative can place the same PC."

`UC-12` (SRS:1225): "Edit floor plan (P4). Administrator. Flow: open room layout → drag/snap PCs → save; viewers see live updates."

### 6.2 SDD §25 — Interactive Floor Plan Architecture

Names the exact four services to build: RoomLayoutService (versioned layouts, one active per room, DB-enforced), AssetPositionService (positions, unique per layout+PC, coords ≥ 0), CoordinateService (snap-to-grid / rotation / z-index math), FloorPlanService (orchestration). Confirms admin-only editing, the colour+label rule, versioning, and the keyboard alternative.

`DD-16` (SDD:1257) — the complete text: "Reverb for real-time (P4) with polling fallback. Live floor plan/notifications; degrade gracefully."

`RES-01` (SDD:465) — Building/Floor/Room CRUD belongs to Locations (P2, already built); FloorPlan keeps only the visual/spatial services.

### 6.3 The original client brief

PROJECT_BOOTSTRAP.md:492-566 is the authority all the above derives from. It specifies drag-and-drop, snap-to-grid, zoom/pan, save layouts, real-time updates, status-coloured icons for the five named states, and the info panel contents:

PC Name · Laboratory · Current Status · Assigned Technician · Complete

Specifications · Installed Hardware · QR Code · Repair History · Upgrade History ·

AI Prediction · Ticket History · Maintenance Timeline

And, decisively for this action:

**"Teachers and technicians will not have this access. Only the admin will have

this feature."** — PROJECT_BOOTSTRAP.md:566

The frontend brief (:568-628) additionally names: Interactive Canvas, Drag and Drop, Zoom, Pan, Minimap, Right-click Context Menus, Information Side Panels, Asset Layer Rendering, Grid System.

### 6.4 The one prior Phase 2.8 scope statement

projectreports/2026-09-07-WP-2.7e-Planning-and-Readiness-Report.md:677-695, §23 "Phase 2.8 boundary" — recorded as a boundary marker and explicitly "not treated as finalised requirements":

admin-only whole-floor visualization; real laboratory/floor layouts; PC/asset

placement; drag-and-drop; snap-to-grid; rearrangement; status visualization by

colour plus shape plus label; asset details; layout persistence; layout

version/history; keyboard/non-drag placement; accessibility; live multi-viewer

synchronization; Laravel Reverb; real-time position/status changes;

concurrent-editing considerations; audit/history; responsive and gamified

visualization.

This is the origin of the terms "gamified", "rearrangement" and "concurrent-editing" in the current brief. They were named, but never converted into requirements.

## 7. Requirements that are new, inferred or unknown

Per the action's §25 classification.

Category 1 — explicitly previously specified: everything in §6.1–6.3 above.

Category 2 — already prepared in code/schema: tables, indexes, CHECKs, models, factories, demo data, permissions, settings, PcStatus, the seam folders, the sequence diagram, FloorPlanVisual.tsx.

Category 3 — inferred implementation detail (labelled, not requirements): fit-to-room / reset-view controls; polling interval; optimistic UI reconciliation; SVG-versus-canvas choice; uuid route keys for room_layouts.

Category 4 — new proposals in the current brief, with no prior basis: room geometry (walls, desks); map-level asset search and status filtering; a minimap promoted from "architecture readiness" to a deliverable.

Category 5 — genuinely unknown, never mentioned by anyone:

An exhaustive search of docs/ returned zero occurrences of "undo", "redo", "optimistic locking" or "version conflict" in any floor-plan context.

undo / redo — never specified.

concurrency strategy — named once as a "consideration", never decided.

canvas-bounds containment — recommended in the design review, never implemented.

uuid route keys / soft deletes on the two tables — never discussed.

API route shapes — never specified.

There is no `OI-*` open issue against the floor plan, real-time, or accessibility. The register (SRS:1588-1606) holds OI-01…OI-11, none of which touch this feature. Conclusion: the floor-plan requirements were baselined without any unresolved client decision recorded against them. Anything decided now is genuinely new, not re-litigation.

## 8. Functional specification

### 8.1 Coordinate system

| Concern | Specification |
| --- | --- |
| Space | Layout-local pixels, origin top-left, matching room_layouts.width/height. |
| Storage | decimal(10,2) as migrated — exact, no floating-point drift. |
| Lower bound | pos_x >= 0, pos_y >= 0 — already enforced by the DB CHECK. |
| Upper bound | pos_x <= layout.width, pos_y <= layout.height — application-layer, per the deferred design-review recommendation. |
| Snap | round(v / grid_size) * grid_size, then clamped to bounds after rounding. |
| Authority | The server snaps and clamps. The client's snap is a preview only. This matches the P4 diagram exactly. |
| Grid source | room_layouts.grid_size is authoritative per room; floor_plan.default_grid_size seeds new layouts; floor_plan.snap_to_grid is the default editor toggle, overridable per session. |
| Rotation / z-index | Columns exist and are persisted; editing them is deferred (see §13). |

### 8.2 Data model changes — two additive migrations, no destructive change

Migration A — public route keys (required). Add uuid to room_layouts following the exact established pattern of 2026_07_26_100000_add_uuid_to_floors.php: nullable + gen_random_uuid() default → explicit backfill → NOT NULL + unique index, plus HasUuidRouteKey on the model. Positions are addressed through the layout uuid + PC uuid pair, so floor_plan_positions needs no uuid of its own.

Migration B — concurrency (only if D3 selects a stored token). Recommended alternative: use the existing updated_at as the precondition token, which requires no migration at all.

No other schema change is required. Specifically:

Position history needs no table — activity_logs + properties (DD-55).

Layout versioning needs no table — room_layouts.version plus the existing

partial unique index already model it.

### 8.3 Backend — filling the existing App\Domains\FloorPlan scaffold

Follows the Locations/Assets idiom exactly: thin controller → Action → Resource, with Services owning invariants.

Domains/FloorPlan/
  Services/   CoordinateService      snap / clamp / bounds maths (pure, unit-tested)
              RoomLayoutService      versioning, activation, one-active invariant
              AssetPositionService   position upsert, conflict detection
              FloorPlanService       read-model assembly for the map
  Actions/    UpsertAssetPosition · CreateRoomLayout · ActivateRoomLayout · RemoveAssetPosition
  Http/Controllers/Admin/   FloorPlanController · RoomLayoutController · AssetPositionController
  Http/Requests/            UpsertAssetPositionRequest · StoreRoomLayoutRequest
  Http/Resources/           FloorPlanResource · RoomLayoutResource ·
                            FloorPlanPositionResource · FloorPlanPcResource
  Policies/                 RoomLayoutPolicy · FloorPlanPositionPolicy

The service names are taken from SDD §25, not invented.

Both policies must be registered in AppServiceProvider::registerAuthorization() — the project registers every policy explicitly there.

Enum additions: PcStatus::label() and PcStatus::tone() mirroring AssetStatus; and a // Phase 2.8 — Interactive Floor Plan block in ActivityAction: layout_created, layout_activated, layout_updated, asset_position_changed, asset_position_cleared.

### 8.4 API design

All under the existing chain: auth:sanctum → active → AuthenticateSession → password.current → prefix('admin') → whereUuid([...]).

| Method | Route | Gate |
| --- | --- | --- |
| GET | /admin/floor-plan/floors/{floor:uuid} | can:floorplan.manage |
| GET | /admin/floor-plan/rooms/{room:uuid} | can:floorplan.manage |
| GET | /admin/floor-plan/rooms/{room:uuid}/updates?since=<iso8601> | can:floorplan.manage |
| POST | /admin/floor-plan/rooms/{room:uuid}/layouts | can:floorplan.manage |
| POST | /admin/floor-plan/layouts/{layout:uuid}/activate | can:floorplan.manage |
| PATCH | /admin/floor-plan/layouts/{layout:uuid}/positions/{pcUnit:uuid} | can:floorplan.manage |
| DELETE | /admin/floor-plan/layouts/{layout:uuid}/positions/{pcUnit:uuid} | can:floorplan.manage |

PATCH body: { pos_x, pos_y, rotation?, z_index?, expected_updated_at? }. The response returns the server-snapped position so the client reconciles to truth.

The updates endpoint is the DD-16 polling channel, and is deliberately shaped so its payload is identical to the future broadcast event — the Reverb upgrade then swaps only the transport.

(Gating reads on `floorplan.manage` rather than `floorplan.view` is what makes the feature admin-only without touching seeded permissions — see D2.)

## 9. UX / UI and digital-twin interaction specification

Render with inline SVG + React, adding no new dependency. This is not a compromise; it is the project's demonstrated instinct. Phase 2.4 rendered dashboard distributions with "no charting dependency, no colour-only encoding", and FloorPlanVisual.tsx already renders this exact picture with hand-rolled positioned nodes. At the real scale — 24 PC units total, ~5–20 per room — a canvas library, virtualization and WebGL are all premature. SVG additionally gives keyboard focus, aria-* and text labels for free, which a <canvas> would have to reimplement to satisfy FR-FP-009.

features/floor-plan/
  api/floorPlanApi.ts
  hooks/queries.ts       floorPlanKeys.{all,floor,room,updates}
  hooks/mutations.ts     useUpsertPosition — optimistic, rolled back on error,
                         reconciled to the server's snapped coordinates
  stores/useFloorPlanStore.ts   viewport (zoom/pan), selection, move-mode, snap
                                toggle — ephemeral only, never server truth
  components/  FloorPlanCanvas.tsx    <svg> viewBox pan/zoom, grid <pattern>
               PcNode.tsx             focusable node: colour + icon + label
               FloorPlanToolbar.tsx   zoom, fit, reset, snap toggle, grid size
               MovePanel.tsx          the non-drag placement control (FR-FP-009)
               PcInspectorPanel.tsx   FR-FP-005 details
               FloorPlanLegend.tsx    reuses StatusPill
  pages/FloorPlanPage.tsx
  types.ts

Zoom/pan via the SVG viewBox — one attribute, no library, no layout thrash.

Grid via <pattern>, sized from layout.grid_size.

Drag via native pointer events with setPointerCapture; a drag preview carries

a shadow, which the Flat-Plane Rule explicitly sanctions.

"Gamified" is interpreted as a spatial, responsive, immediately-legible map with

smooth movement, hover/focus affordances and clear state — not game mechanics, points or avatars. The asset data remains the source of truth.

Wiring is three edits, matching existing convention: a lazy() route in App.tsx wrapped in RequirePermission; one NAV_ITEMS entry in layouts/AppLayout.tsx; one route added to e2e/specs/a11y.spec.ts.

Shell constraint: AppLayout has no sidebar — horizontal sticky nav, and <main> is full-bleed single-column, which suits a wide canvas.

### 9.1 Asset detail panel (FR-FP-005)

Uses only existing domain data, drawn from the bootstrap's own list: unit code / PC name, asset tag, room, status + label, specifications (pc_specifications), installed hardware (pc_component_installations), QR code, assigned technician, active ticket and ticket history, maintenance timeline, last maintenance, warranty. AI predictions are P3 and therefore out of scope.

## 10. Accessibility specification

Accessibility is why SVG was chosen, not a later polish pass. Targets NFR-ACC-008, WCAG 2.2 2.5.7 Dragging Movements, 2.1.1 Keyboard, 2.5.8 Target Size.

Every PC node is a focusable <button> in the tab order whose accessible name

carries identity + status + position — e.g. "PC-07, under maintenance, column 4, row 2".

Move mode is the non-drag equivalent: focus a node → Enter/Space enters move

mode → arrow keys nudge one grid cell (Shift+arrow = one pixel) → Enter commits, Escape cancels and restores the original position.

MovePanel provides numeric X/Y entry as a third, pointer-free path.

A role="status" aria-live="polite" region announces each committed move, following

the existing UnreadAnnouncer.tsx pattern.

Status is never colour-only: colour + icon shape + text label (FR-FP-004,

NFR-ACC-004, the StatusPill contract).

Toolbar controls are real buttons with labels; zoom offers explicit +/−/Fit/Reset

rather than wheel-only. Targets ≥ 44×44 px.

The global :focus-visible 3px ring at 2px offset already applies

(frontend/src/index.css:253).

usePrefersReducedMotion suppresses node transitions (NFR-ACC-005).

Room/floor navigation reuses the LocationTree precedent: *"a native nested list

with aria-expanded buttons rather than a treeitem widget"*.

Inherited gap, reported not silently fixed: Drawer and Modal implement no

focus trap and no focus restore. The inspector panel should therefore be a

non-modal side region, which sidesteps the gap and matches the WP-2.7b decision

to make the notification panel non-modal.

## 11. Real-time synchronisation specification

Presentation build — polling, under DD-16.

GET /admin/floor-plan/rooms/{room:uuid}/updates?since=<iso8601> returns positions and PC statuses changed since the timestamp. The client polls on a ~5 s interval, paused while the tab is hidden and while a drag is in flight.

This satisfies FR-FP-007's observable behaviour — Administrator B sees Administrator A's move without refreshing — with zero new containers, zero nginx changes, zero CSP changes, and no risk to the production image.

| Concern | Handling |
| --- | --- |
| Authorization | The endpoint is gated identically to every other write path. |
| Ordering | Server updated_at is authoritative; the client applies by timestamp. |
| Duplicate events | Upsert semantics make re-application idempotent. |
| Stale clients | since is always the last successfully applied server timestamp. |
| Reconnect | Trivial — the next poll carries since; no session to re-establish. |
| Optimistic UI | Applied locally, then reconciled to the server's snapped answer. |
| Conflicts | Per D3 — recommended expected_updated_at → 409. |

Post-presentation — Reverb (`WP-4.1`). Private channel private-floor-plan.room.{roomUuid}, authorized in a new routes/channels.php against the floor-plan permission. Proxy Reverb through the same nginx origin (for example /reverb) to preserve the project's single-origin Sanctum architecture and keep connect-src 'self' valid. Add the service to both compose files; rebuild the production image; update the CSP regression test.

PostgreSQL remains the source of truth in both modes; Reverb is a transport.

## 12. Security model

Admin-only enforced in the backend, not the UI: every route carries

can:floorplan.manage, and each policy re-checks per record.

Route gate + policy + action — the project's three-layer chain; Gate::before

resolves permission strings, so an unregistered policy fails open. Registration in AppServiceProvider is mandatory.

Coordinate bounds validated server-side against the layout's own

width/height — the DB only guarantees >= 0.

Room-ownership validation: the PC unit must already belong to the layout's room.

This blocks cross-room reassignment through the position endpoint, which would otherwise be an asset-transfer path bypassing assets.transfer.

Active-layout requirement: edits are accepted only against the room's active

layout.

UUID route keys only — numeric ids are never addressable (NFR-SEC-001,

AC-G2), which is why Migration A exists.

Auditability: every accepted move writes an activity_logs row with actor, IP,

user agent and before/after coordinates.

CSRF/auth consistency: inherits the existing Sanctum single-origin cookie flow

and the password.current middleware already applied to every admin route.

IDOR: per CLAUDE.md §6, a room absent from a user's list must be equally

unreachable by direct UUID — asserted by test, not assumed.

## 13. Scope classification

Legend — EP existing preparation · NEW required new work · OD owner decision · OPT optional enhancement · OOS out of scope.

| Item | Evidence | Priority | Disposition |
| --- | --- | --- | --- |
| Whole-floor / room / PC visualisation (FR-FP-002) | Specified | CRITICAL | NEW |
| Status colour + shape + label (FR-FP-004) | Specified + prototype | CRITICAL | NEW (EP visuals) |
| Admin-only enforcement | Brief says admin-only; SRS grants technician view | CRITICAL | OD (D2) |
| Drag-and-drop placement (FR-FP-003) | Specified | CRITICAL | NEW |
| Snap-to-grid (FR-FP-003) | Specified + settings seeded | CRITICAL | NEW (EP config) |
| Server-side bounds validation | Design review, deferred | CRITICAL | NEW |
| Keyboard / non-drag placement (FR-FP-009) | Specified | CRITICAL | NEW |
| Layout persistence | Schema exists | CRITICAL | NEW (EP schema) |
| Pan / zoom (FR-FP-002) | Specified | HIGH | NEW |
| Asset info panel (FR-FP-005) | Specified + brief field list | HIGH | NEW |
| Layout versioning (FR-FP-001/008) | Specified; columns + index exist | HIGH | NEW (EP schema) |
| Position history / who moved what | DD-55 precedent; AuditLogger exists | HIGH | NEW (EP mechanism) |
| Live updates (FR-FP-007) | Specified; DD-16 permits polling | HIGH | NEW — polling first |
| Reverb transport | Specified as target; WP-4.1 | MEDIUM | Post-presentation |
| Concurrency strategy | Named once, never decided | HIGH | OD (D3) |
| Undo / redo | Never specified anywhere | LOW | OD (D5) — recommend OOS |
| Fit-to-room / reset view | Inferred from pan/zoom | MEDIUM | NEW (cheap) |
| Minimap | Brief + seam README; no FR | LOW | OPT |
| Right-click context menu | Brief + seam README; no FR | LOW | OPT |
| Map search / status filter | No prior basis | MEDIUM | OPT |
| Rotation + z-index editing | FR-FP-003 names both; columns exist | MEDIUM | Deferred — persist, don't edit |
| Background image upload | FR-FP-001; column exists | LOW | Deferred |
| Room geometry (walls, desks) | Brief only; no FR, no schema | MEDIUM | OD (D6) |
| Technician read-only view | FR-FP-006 | MEDIUM | Deferred (per D2) |
| AI predictions on the panel | P3 | — | OOS |
| Network topology, heat maps, density, indoor nav | FR-FP-010, class Future | — | OOS |

## 14. Package breakdown

Proposed as sub-packages of the existing `WP-4.2` / `WP-4.3` rather than a new number, with `WP-4.1` (Reverb) deliberately resequenced to last.

### P2.8-a — Domain foundation (no UI)

Objective: CoordinateService (snap/clamp/bounds), RoomLayoutService, uuid route key on RoomLayout, both policies registered, PcStatus::label()/tone(), new ActivityAction cases. Database: Migration A — additive, reversible (32 → 33). Testing: unit tests for coordinate maths; FloorPlanAuthorizationTest asserting 403 for technician and teacher on every route. Security: establishes the permission gate. A11y: none. Deploy: none. Risk: low. Depends on: nothing.

### P2.8-b — Read API and the map (presentation-critical)

Objective: floor/room GET endpoints, resources, FloorPlanCanvas with SVG pan/zoom/grid, status-coloured PcNode, legend, route and nav entry. Testing: feature tests for payload shape and redaction against the encoded payload; Vitest for node rendering and status labels. A11y: focusable nodes, accessible names, axe baseline entry. Risk: low. Depends on: a.

### P2.8-c — Placement: drag, snap, keyboard (presentation-critical)

Objective: PATCH/DELETE position endpoints with server-side snap, bounds and same-room validation; pointer drag; move mode + `MovePanel`; optimistic update reconciled to the server. Security: cross-room movement and out-of-bounds coordinates rejected server-side. A11y: this package is FR-FP-009. Testing: authorization (403 by role), bounds (422), cross-room rejection, Vitest keyboard-move test, axe scan with a node selected. Risk: medium — interaction polish. Depends on: b.

### P2.8-d — Persistence, versioning, history (presentation-critical)

Objective: layout create/activate honouring the one-active index; activity_logs rows carrying {from:{x,y}, to:{x,y}, layout_version} via AuditLogger (DD-55 — no new table); history surfaced on the inspector panel. Testing: assert the activity row and its properties; assert the database rejects a second active layout. Risk: low. Depends on: a, c.

### P2.8-e — Live updates by polling (presentation-critical, DD-16)

Objective: the updates?since= endpoint and the client poller, payload shaped as the future broadcast event. Testing: two-client feature test — A moves, B's updates call reports it. Risk: low. Depends on: c.

### P2.8-f — Verification and production parity (presentation-critical)

Objective: the full gate; Playwright e2e for the admin map; axe baseline entry; production image rebuild and the same behaviour confirmed on `:8081`; the documentation reconciliation of §15. Deploy: this is the deployment package. Risk: medium-high — the production image predates Phase 2.7, so this rebuild also ships 2.7. Depends on: all.

### P2.8-g — Reverb transport (POST-PRESENTATION — SPMP `WP-4.1`)

Objective: laravel/reverb, routes/channels.php, ShouldBroadcast, laravel-echo + pusher-js, a compose service in both stacks, nginx WebSocket proxying, the production CSP and its regression test, image rebuild. Risk: high — four coupled infrastructure surfaces. Depends on: e. Explicitly excluded from the presentation build.

## 15. Documentation impact (at phase close, not now)

Documents are frozen at Version 1.0 by client instruction — amend in place, never bump the label, and record the change in each revision-history table.

SRS — mark FR-FP-001..009 delivered or partial with the phase tag; record that

FR-FP-007 is met by the DD-16 polling fallback with Reverb outstanding; record the D2 resolution; note rotation/z-index editing, background images and the technician view as deferred. Update the §8.4 permission matrix only if D2 changes a role's grants.

SDD — rewrite §25 from "Data/seams exist; no logic yet" to the delivered

architecture; add DD-* entries for SVG-over-canvas, server-authoritative snapping, activity-log-as-position-history (extending DD-55), the concurrency choice, and polling-before-Reverb under DD-16. Update §14.1 implemented-vs-planned. Caution: the SDD text stops at DD-57 while DD-58..66 are cited by the SRS/SPMP but absent — a known open documentation gap. New numbering must not collide.

SPMP — mark WP-4.2/WP-4.3 progress, record the P4-advanced-ahead-of-P2-GA

decision and the WP-4.1 resequencing, and add a revision-history entry.

Repository notes — correct the two stale claims in

backend/app/Domains/FloorPlan/README.md (§4).

Marketing copy — per D8.

## 16. Risks

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Reverb's four-surface deployment cost consumes the schedule | High | Polling under DD-16 for the presentation; Reverb as P2.8-g. |
| Production rebuild ships Phase 2.7 and 2.8 together (prod at 30 of 32 migrations) | High | Resolve D7 immediately; rehearse deploy-prod.sh / rollback-prod.sh. |
| WP-4.1's documented "P2 GA" dependency is being bypassed | High | Record explicitly via D1; do not let it pass silently. |
| Marketing copy promises Reverb by name while the build polls | Medium | D8 — adjust copy or accept a knowingly forward-looking claim. |
| Admin-only conflict between the brief and the SRS | Medium | D2 — gate on floorplan.manage, changing no permission. |
| Drag polish overruns the deadline | Medium | Keyboard/MovePanel ships in P2.8-c, so a drag regression never blocks the demo. |
| Demo data is visually thin (all PCs in one row) | Low | Improve DemoSeeder positions, or arrange live during the demo — which itself demonstrates the feature. |
| Working tree carries 21 modified files, uncommitted; origin ends at c9ab8a4 | Medium | Resolve the current tree's disposition before starting P2.8-a. |
| @playwright/test / @axe-core/playwright used by e2e/ but absent from package.json (supplied by the Docker image) | Low | Pre-existing; reported, not fixed — outside this scope. |

## 17. OWNER DECISIONS REQUIRED

| # | Decision | Recommendation |
| --- | --- | --- |
| D1 | P4 is being advanced ahead of remaining P2 and all of P3, and WP-4.1's "P2 GA" dependency bypassed. Confirm. | Proceed, recorded as an explicit client decision in the SPMP. |
| D2 | The original brief says admin-only; the SRS (FR-FP-006) grants technicians `floorplan.view`, and they hold it today. | Gate the entire feature on `floorplan.manage`. It is then admin-only in effect, with no permission change and no SRS amendment; the technician view is recorded as deferred. |
| D3 | Concurrency: last-write-wins vs optimistic concurrency. Never decided. | Optimistic via `expected_updated_at` → 409. No migration, demos well, prevents silent clobbering. |
| D4 | Read floor_plan.* settings at runtime, or treat room_layouts.grid_size as sole authority? | grid_size authoritative; read the two settings with the existing ad-hoc helper idiom as defaults. Do not build a settings layer in this phase. |
| D5 | Undo/redo — never specified anywhere. | Out of scope. Escape cancels an in-flight move; the activity log answers "what changed". |
| D6 | Room geometry (walls, desks) — in the brief, but no FR and no schema. | Defer. Ship the grid plus the existing optional background_image. Real geometry needs new schema and its own decision. |
| D7 | Is a production deployment in scope for the presentation? Rebuilding ships 2.7 + 2.8 together. | Decide now — it is the schedule's largest unknown. |
| D8 | The landing page promises real-time "over Laravel Reverb". Polling ships instead. | Soften the copy to "live updates" for the presentation, or accept the claim as forward-looking. |

## 18. Presentation-critical vs post-presentation scope

Presentation-critical (P2.8-a … f): admin-only floor and room visualisation · PCs positioned on the layout · status by colour + shape + label · pan/zoom/fit/reset · drag-and-drop with snap-to-grid · keyboard and numeric placement · server-validated persistence · layout versioning and move history · asset inspector panel · multi-viewer live updates by polling · full quality gate · production parity.

Post-presentation: Reverb transport (WP-4.1) · rotation and z-index editing · background-image upload · minimap · right-click context menus · map search and filtering · technician read-only view · room geometry · AI predictions (P3) · FR-FP-010 in full.

## 19. Recommended implementation order and the first checkpoint

Order: a → b → c → d → e → f, then g after the presentation.

### Exact first implementation checkpoint — P2.8-a, step 1

The smallest reviewable unit: no UI, no behaviour change, fully reversible.

backend/database/migrations/2026_09_28_100000_add_uuid_to_room_layouts.php —

copy the structure and comment style of 2026_07_26_100000_add_uuid_to_floors.php.

backend/app/Models/RoomLayout.php — add HasUuidRouteKey.

backend/app/Domains/FloorPlan/Services/CoordinateService.php — pure snap(),

clamp(), isWithinBounds().

backend/tests/Unit/FloorPlan/CoordinateServiceTest.php — grid rounding at

boundaries, negative rejection, clamping at width/height, grid_size = 1.

Verify: docker compose exec -T app php artisan migrate (development only) · ./vendor/bin/pest --filter=Coordinate · pint --test · phpstan analyse.

Then stop and report before any controller, route or component is written.

## 20. Verification strategy

# Backend
docker compose exec -T app ./vendor/bin/pest
docker compose exec -T app ./vendor/bin/pint --test
docker compose exec -T app ./vendor/bin/phpstan analyse --no-progress --memory-limit=1G

# Frontend
docker compose exec -T node sh -lc "cd /app && npx tsc -b"
docker compose exec -T node sh -lc "cd /app && npm run lint && npm run format:check"
docker compose exec -T node sh -lc "cd /app && npm run test"
docker compose exec -T node sh -lc "cd /app && npm run build"

# Browser + accessibility
sh scripts/e2e.sh
sh scripts/e2e.sh --project a11y

# Production parity (P2.8-f)
docker compose -p sccit_prod -f compose.prod.yaml exec -T app_prod php artisan migrate:status

Per CLAUDE.md §6: a dedicated FloorPlanAuthorizationTest asserting the negative cases role by role; and because the map is room-scoped, assert that a room absent from a user's list is equally unreachable by direct UUID — a list filter without the matching single-record check is an IDOR. Redaction is asserted against the encoded payload. Pest runs must be serialised — the project shares one test database.

## 21. Reconnaissance integrity statement

This action was read-only. No source file, migration, test, configuration, Docker file, document, database row or Git reference was created, modified or deleted. Database access was limited to SELECT counts and a role-permission read. No container was started, stopped or rebuilt. Nothing was staged, committed or pushed; HEAD remains d05fd60.

Phase 2.8 is not implemented and is not authorized. Awaiting explicit approval of the scope and the eight owner decisions above.